TECHNICAL ADVISORY SERVICE 5MMSCFD MINI-LNG PLANT SOUTH ATLANTIC LNG WEST AFRICA LIMITED SERVICE PROPOSAL

|  | Proposal valid until 31.05.2026 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 06.02.2026 | 20877-ILF-NGR-OD-00001 | ¦ | Revision 0 | © |  |  |

REVISION

| 0 | 06.02.2026 | Issued for use | N. Nworgu | M. Olaleye | A. Oshodi |
| --- | --- | --- | --- | --- | --- |
| Rev. | Date | Purpose | Prepared | Checked | Approved |

YOUR POINT OF CONTACT WITHIN ILF

ABIODUN OSHODI

ILF Engineers Nigeria Ltd.

TCF Tower, 33 Adeola Hopewell Street

Victoria Island, Lagos, Nigeria

Tel.: +234 / (0) 1 453 7015/ 7016

mailto: Abiodun.Oshodi@ilf.com

www.ilf.com

TABLE OF CONTENTS

1	INTRODUCTION	6

1.1	Background	6

1.2	Request for Proposal	6

1.3	Purpose of this document	6

1.4	Validity of Offer	6

1.5	Objective of the proposed service	7

2	GROUP PROFILE & PHILOSOPHY	8

3	WORKING EXPERIENCE IN THE REGION	11

3.1	References	14

4	SCOPE OF SERVICE	15

4.1	General Outline	15

5	ILF’s APPROACH	16

6	METHODOLOGY	17

6.1	Proposed Methodology and Work Plan	17

6.2	Pre-Construction Due Diligence	18

6.3	EPC Contract	18

6.4	Engineering Design Review	19

6.5	Procurement Supervision	20

6.6	Construction Monitoring	20

6.7	Close-out Report	23

6.8	Optional Services	23

6.9	Location	24

6.10	Key Resources	25

6.11	Safety on Site	28

7	COMMERCIAL PROPOSAL	29

7.1	Payment Schedule	30

7.2	Reimbursable Rates	30

7.3	Non Labour Costs	31

8	REQUIRED CLIENT INPUT AND ASSUMPTIONS	32

9	ASSUMPTIONS AND EXCLUSIONS	33

9.1	Exclusions from Services	34

10	CONTRACT	35

10.1	Contractual Liability Cap	35

10.2	Project Language	35

10.3	Exclusion of Consequential Damages	35

11	CONCLUSION	36

12	ATTACHMENTS	37

LIST OF TABLES

Table 1: Project References	11

Table 2 – Key resource	25

Table 3: Reimbursable Rate	30

FIGURES

Figure 1 - ILF offices worldwide	8

Figure 2: Technical Advisory Services.	17

Figure 3:Preliminary Execution Strategy .	26

Figure 4: Manning Chart.	27

# INTRODUCTION

## Background

South Atlantic LNG West Africa Limited (“the Client” or “SA LNG”) is an indigenous company located in Lagos Nigeria with specialized skills providing ancillary services to the power and oil & gas sectors in Nigeria.

The client is proposing to build a 5MMSCFD Mini-LNG Plant in Ibefun axis and have received a firm offer from a Chinese EPC contractor for the FEED, Detailed Engineering, Procurement and Fabrication, Construction and Installation works. Client’s proposed timeline is 16 months.

Client has also secured equity financing from the Midstream and Downstream Gas Infrastructure Fund (MDGIF).

## Request for Proposal

The Client has asked ILF (the Consultant) to provide “Project Management and Consultancy Services - PMC” service for the development / construction of a 5MMSCFD Mini-LNG Plant in the Ibefun area (the project).

In further conversation with the Client and in consideration of client’s budget, ILF is proposing to offer “Technical Advisory – TA” for the EPCI for the 5MMSCD Mini-LNG Plant (“Project”).

## Purpose of this document

This document is ILF’s proposal demonstrating ILF’s capabilities, scope of service, consultant’s experience, execution methodology and available key resources to provide services for the project.

## Validity of Offer

Our proposal is valid for One Hundred and Eighty (180) days from the date of this proposal.

## Objective of the proposed service

The services detailed in this proposal will achieve the following;

- Safety: Ensure the safety of the facility’s function and that project execution methodology is environmentally acceptable and considers human factors in its implementation.

- Cost Efficiency: ILF will ensure that its service will support efficient utilization of budget cap for project development.

- Certified Design Standards: ILF’s services will meet the most stringent Nigerian regulatory standard, COMPANY guide, practices & specifications and industry odes & Standards.

- Compliance with Standards: ILF’s works are consistent with operational reliability and safety philosophy.

# GROUP PROFILE & PHILOSOPHY

“ILF combines local presence and international expertise to best serve clients’ needs.”

Klaus Lässer, CEO

ILF is a leading independent international multi-disciplinary engineering and consulting company offering a broad range of services on major industrial and infrastructural projects worldwide for over 55 years. With over 2,500 highly qualified employees in more than 45 office locations across five continents, the companies of ILF have a strong global presence. ILF combines excellent consulting expertise and a broad international background with project-specific expertise and an in-depth understanding of local requirements due to a stable, long-established presence in its markets. It is completely independent with no affiliation to construction firms, suppliers or financial institutions. Objectivity through independence is a key aspect of its business philosophy.

55+

years of experience

2 500+

employees worldwide

9 500+

projects successfully executed

150+

successful project execution countries

45+

offices across five continents

ILF at a glance

ILF management procedures are ISO 9001, 14001 and OHSAS 18001 certified.

Figure 1 - ILF offices worldwide

ILF has executed more than 9,500 projects successfully in over 150 countries. The company has over 55 years of experience in the energy and oil and gas sectors worldwide, by providing comprehensive services for major industrial and infrastructure projects in the following business areas:

Energy & Climate Protection

Water & Environment

Transportation & Urban Spaces

Oil, Gas & Industrial

ILF primarily employs consulting engineers with expertise in electrical, civil, mechanical, process, instrumentation and economic engineering/business administration who are capable of providing a wide range of engineering, project management and consultancy services through all project development phases from early conceptual and feasibility studies, including Master Plans, through planning and design to construction and commissioning and ultimately operations.

Across its offices, ILF has staff in a large variety of other disciplines, such as business administration, geology, environment protection, chemistry and many others. Apart from technical scope, many projects typically have significant commercial, economic and regulatory aspects that need to be addressed by customizing project services. ILF Group offers a comprehensive set of services for the energy industries related to project finance, merger & acquisition, project management and capacity building.

In more detail the ILF's Services comprise:

feasibility studies for power and oil & gas facilities, such as power plants, processing facilities (including petrochemical), pipelines, loading facilities and other relevant installations

sound cost estimates for oil & gas facilities based on 50 years of project experience

physical planning of infrastructure installations, FEED and the following detailed design, and management of the development and commissioning of the new facilities

the setup of management and operational systems to the point that the new facility becomes an independent functional entity

comprehensive risk assessments addressing process safety as well as occupational health & safety and environment, and development of emergency response plans

supporting vendors and investors during the divestiture / acquisition phase by assessing the value, inherent strengths and associated risks of the assets in question

assignments as lender's engineers where our experts estimate the construction budget and schedule from an in independent perspective and check whether borrower’s assumptions are reasonable and include the proper level of contingencies

due diligences developing detailed operational and business plans as well as comprehensive financial models serving as base case model for project finance

carrying out workshop and in-house training, e.g. on financial modeling, project management or contract and claims management

Vision, Values & Beliefs

ILF passionately devotes its energy to pursuing the vision of improving the global quality of life. This is what drives the company and makes its employees believe in their work.

It is motivated by its ambition to achieve market leadership through quality. This is why it focuses on a structured approach to problem solving and is constantly striving to improve. But above all, it is its great people that really make the difference. They truly believe in respect, honesty, reliability and fairness as a solid foundation for all our interactions.

ILF continues to spearhead Engineering Excellence. Its independence allows it to provide creative solutions while continuously acting in every client’s best interest.

# WORKING EXPERIENCE IN THE REGION

ILF is qualified and has demonstrated experience in the assignment through its broad range of project experience located in Western Africa. Our local presence in Lagos, Nigeria and in Accra, Ghana offers both local and regional expertise and is strengthened by its global reach of experts across ILF’s over 45 offices worldwide. Our recent projects involving Technical Consultancy scope projects in West Africa are:

Table 1: Project References

| S/No. | PROJECT DESCRIPTION | PROJECT LOCATION | PROJECT DURATION | CLIENT |
| --- | --- | --- | --- | --- |
| 01 | Ajaokuta - Kaduna - Kano Gas Pipeline PMC Services | Lagos, Nigeria | Jan., 2020 - Ongoing | NNPC-Nigerian National Petroleum Corporation, Garki, Abuja |
| 02 | Engineering Design and Project Support Services (ESA) | Nigeria | June 2022 - Ongoing | Shell Petroleum Development Company of Nigeria |
| 03 | Rehabilitation of FPSO | Benin, Nigeria | June 2022 - Ongoing | NNPC Exploration and Production Limited |
| 04 | Gas Pipeline Network – Vendor Due Diligence | Nigeria | July, 2020 – July, 2021 | Axxela |
| 05 | Technical Environnemental Due Diligence ¦ Hydrocarbon Infrastructure | Nigeria | Nov, 2020 – Jan, 2021 | Petrolex |
| 06 | Consultancy Services for the Proposed Regional Gas Transmission Pipeline from Benin Republic - Niger Republic | Cotonou, Benin Republic | Jan., - May, 2020 | Benin LNG Company |
| 07 | Gbarain Power Plant - Shoreline Protection of NIPP 18’’ X 1.5Km Gas Pipeline | Lagos, Nigeria | Mar., 2020 - Ongoing | Niger Delta Power Holding Company Limited |
| 08 | 210 MTD Mini LNG project, Nigeria, Risk Assessment | Lagos, Nigeria | Jan – May 2020 | Confidential |
| 09 | 10 MW Kano Solar Power Project - Consultancy Services, Energy audit and Power evacuation studies | Nigeria | 2019 - 2020 | NSIA |
| 10 | Technical Due Diligence on Gas Processing Plant | Lagos, Nigeria | Feb., - Mar., 2019 | Africa Plus Partner |
| 11 | Sublime LPG Terminal Lekki-Nigeria, Review of Technical Pre-Feasibility Study | Lagos, Nigeria | Nov. 2017 – Nov. 2019 | Xploil Nigeria Limited / Nigeria |
| 12 | Technical Due Diligence Study for Axxela Group Assets | Lagos, Nigeria | Feb., - Mar., 2019 | Elektron Petroleum Energy and Mining Limited |
| 13 | 210 MTD Mini LNG project, Nigeria, Conceptual Design and FEED | Lagos, Nigeria | June 2019 – Oct 2019 | Confidential |
| 14 | Conversion of a Simple Cycle to Combined Cycle Power Plant - Lender’s Advisor, Technical and Commercial Due Diligence | Ghana | Oct, 2015 – Jan 2018 | Lending Bank (Confidential) |
| 15 | 10 Power Plants (Gas Engine driven) 60 MW Captive Power Generation Portfolio, Tricap Nigeria _ Technical Due Diligence, Feasibility Study | Nigeria | Mar – Oct, 2015 | Financial Investor (Confidential) |
| 16 | Value for Money analysis – Technical, Commercial | Ghana | Mar – Oct, 2015 | Plant Operator (Confidential) |
| 17 | Detailed Design of Ijora LPG Terminal | Lagos, Nigeria | April 2015 - September 2015 | Gas Terminalling Global Operations Limited |
| 18 | Pre-Feasibility Study for an LPG Storage Terminal | Nigeria | May 2015 – July 2015 | Hyde Energy |
| 19 | Design Review of OSPP Tank Farm and Terminal Project | Cotonou, Benin, West Africa | May 2015 - June 2015 | Socar, Switzerland |
| 20 | Multi-product Pipeline from Dangote Jetty and tank terminal, LFTZ to PPMC Mosimi Depot - Concept Study | Lagos, Nigeria | Aug 2014 – Feb 2015 | Dangote |
| 21 | Engineering Design Services for EHPL Early Utilization Pipeline Project | Nigeria | March, 2014 – Aug 2014 | Acugas / Septa Energy |
| 22 | 3 Gas Power Plants – Technical Due Diligence for Investor | Nigeria | Oct, 2013 – Jan, 2014 | Quantum Power-Nigeria |
| 23 | Greater Lagos Gas Distribution Project, GNL, Consultancy Services | Nigeria | Dec., 2013 – April, 2014 | Gaslink |
| 24 | Project Management Consultancy Services for a Marine Jetty, pipeline and distribution facility EPC Contact | Nigeria | May 2012 – June 2014 | Oando PLC |
| 25 | Rehabilitation of an Import Berth Platform and Tank Farm facilities at Escravos | Escravos, Nigeria | April 2012 – Aug 2013 | NNPC |
| 26 | Detailed Engineering Services of Oron Gas Pipeline | Nigeria | May, 2012 – February, 2013 | Acugas / Septa Energy |
| 27 | Due Diligence study for an LPG Terminal | Nigeria | May 2012 – Oct 2012 | Oando PLC |
| 28 | Project Management Services, Seme Field Re-Development Project | Seme, Republic of Benin | February, 2012 – September 2015 | South Atlantic Petroleum Company |
| 29 | Owners Engineers SERVICES FOR JETTY EXECUTION | Nigeria | November 2011 - March 2013 | Oando |
| 30 | Detailed Engineering Services; QIT Flare Gas Elimination Project | Nigeria | June 2011 to May 2012 | Sudelettra Nigeria Limited |
| 31 | Feasibility Study and FEED - Gas Pipeline Distribution | Nigeria | June 2011 - November 2012 | Oando / Gaslink |
| 32 | FEED Services - Seme Field Development – Plem & Admiralty Buoy | Seme, Republic of Benin | July 2011 – Nov. 2011 | EPIC Atlantic /SAPETRO |
| 33 | Rehabilitation of New Atlas Cove to Mosimi 16” Multi-Products Pipeline Project | Nigeria | November 2010 - December 2013 | Nigerian National Petroleum Corporation |
| 34 | Feasibility Study for Petroleum Products Supply & Storage Terminal in the Lekki Free Trade Zone | Lekki Free Trade Zone - Nigeria | March, 2008 – July 2008 | DBN / DBN |
| 35 | Petroleum Products Delivery System from New SPM to Marketers Jetties at APAPA - FEED Engineering | APAPA - Nigeria | August 2007 – February 2008 | OANDO PLC |
| 36 | Petroleum Products Terminal in the Lekki Free Trade Zone or any other Oando selected location | Lagos | August 2007 – January 2008 | Oando PLC |
| 37 | Engineering Design & EIA Study for LPG Facilities | Tamora Island – Lagos | 2007 – 2008 | Linetrale Gas Limited |
| 38 | Revamp of ATLAS COVE Depot Facilities | Nigeria | August, 2006 – September, 2008 | Pipelines and Products Marketing Company |
| 39 | Oben – Ajaokuta – Abuja – Kaduna Gas Pipeline System | Oben – Ajaokuta – Abuja – Kaduna | Nov. 2006 – March 2007 | NGC / POSCO |
| 40 | Rehabilitation of Escravos IBP and Tank facilities | Escravos, Nigeria | 2005 – 2006 | Pipelines and Products Marketing Company |

## References

A process overview demonstrating ILF’s capacity is given in the attachment(s) below:

Attachment 1 – Company Brochures

# SCOPE OF SERVICE

## General Outline

- The TA (Technical Advisor) shall review the projected construction programme, expenditure schedule and adequacy of the arrangements made at the site to achieve the projected construction schedule on a monthly basis;

- The TA shall review, assist, advise and report to the client on the progress of work on a monthly basis, vis-à-vis program of construction and milestone dates specified in the various construction and procurement agreements related to the development of the project;

- Engineering vetting for FEED and Detailed Design – define certain milestones for which the FEED and DED packages will be reviewed.

- Procurement Support – review of procurement packages

- The TA shall carry out spot verification of the quality of the various components of Project vis-à-vis approved specifications;

- The TA shall review quality control tests carried out;

- The TA shall review and assess variation orders;

- The TA shall review adherence to environmental regulations and report on any present / future risks that arise during Project implementation; assess compliance with HSE and environment and social management plan specified in the Facility agreement

- The TA shall bring to the notice of the client any event, which may lead to a Force Majeure event as laid down under contracts related to construction and procurements of various components of the Project, which may lead to time or cost overrun;

- The TA shall review the status of necessary approvals, permits, licenses, notifications, Project completion certificates, etc. as may be required for implementation of the Project;

- Identification and review of cost overruns (if any) and on time over runs (if any) and make recommendation.

- The TA shall from PMC’s and EPC’s monthly report, provide a report to the client.

# ILF’s APPROACH

ILF’s project execution strategy will be governed by the principle to minimize risks that would possibly endanger the most important targets, namely the quality of the work and the budget conformity.

ILF will follow the hereunder listed general principles which will facilitate the execution.

- ILF will assign personnel for this project on a long term basis in order to ensure continuity and synergies.

- All services will be coordinated by ILF’s project management.

- ILF will use latest technology tools for design work review. This ensures transparent and easy change management and minimizes conflicts during construction.

- The technical strategy will be governed by the principle to minimize risks that would possibly endanger the quality or overrun the budget or drastically endanger the foreseen completion date. That involves a close and transparent cooperation with Client, which is in our opinion an absolute must for such a specific project.

- Technical queries will be collected and processed according to the requirements of the contract and discussed and agreed with Client. It is an ILF policy to treat this matter fully transparent to the Client and to agree in close co-operation on the best economical and technical solution.

# METHODOLOGY

## Proposed Methodology and Work Plan

The main contents of the Lender's Technical Consultant either in an integrated team or as an independent consultant shall include as a minimum:

Figure 2: Technical Advisory Services.

ILF intends to perform the services in ILF-NGR Lagos Office. ILF will appoint a Project Manager, who shall be the primary point of contact with Client’s project representatives. The Project Manager will be responsible for the entire project execution, coordination and completion in accordance with the scope of work requirements. This includes all management, contractual, commercial / financial, schedule and technical issues of the project.

Internal quality assurance reviews will be organized and performed by ILF’s quality assurance Engineer in accordance with ILF’s QA system. The QA Engineer advises the Project Manager for appropriate action in case of non-compliance with the established QA systems.

The Subject Matter Experts (SME) are fully responsible for their technical / commercial disciplines to comply with the scope of work, they report directly to the Project Manager. The Project Manager and the SMEs co-ordinate, organise and supervise the back-room discipline personnel who will provide review of documentation and analysis as required by the SMEs.

ILF Engineers Nigeria Ltd. intends to perform the Lender’s Technical Advisory Services in order to achieve the following;

- To provide a review and assess function regarding the planning, monitoring, controlling and coordination activities of the project in achieving the project goal.

In the following description ILF will outline the methodological approach, working plan, work organization and resource staffing with key experts to execute the project according to formulated requirements. The offered services will be performed in close coordination and cooperation with the client.

## EPC Contract

During this phase, the Technical Advisor (TA) shall carry out the following key activities;

- Review EPC Contractor planned execution methodology for practicability.

- Review contract approved vendors and subcontractor list in order to ensure that all aspects of the project scope have been considered and no identifiable conflicts, e.g Procurement, Shipment and Transportation to Site, Pipe Coating, Pipe lay, Non-Destructive Testing, Excavation and other Civil Works, etc.

- Review EPC Contractor project execution schedule for key installation parameters, e.g. procurement lead times, construction sequence etc.

- Confirm that the contract is in line with the specified contract type (FIDIC silver book) and that contract is fixed price, date certain.

- Comment on the adequacy of EPC packaging and reasonableness of contractual terms (e.g. work program, project cost, project delivery milestones and associated payment milestones/amounts, allocation of risks, performance guarantees/warrantees and contingency provisions).

- Verify that the EPC contract has appropriate provisions for Liability Limits, Defects Liability Period(s), Liquidated Damages (LDs) and clear execution plan to meet specification and delivery time.

- Evaluate the potential for scope change or variation orders as well as implications and consequences on Project costs.

- Recommend specific action plan to mitigate any identified risks or conditions of the EPC contract.

- Review project delivery and payment milestones in line with industry standard practices and in addition, assess the adequacy of the EPC submission from the contractor.

- Assess the level of completeness of the EPC Contract documents and ensure provisions have been made to ensure project delivery in line with client objectives.

- Review EPC contractor inspection and test plans in order to ensure that at key hold points, EPC contractor has allowed for external/third party witnessing.

## Engineering Design Review

Front End Engineering Design and Detailed Design are expected to be executed by the EPC Contractor. ILF assumes that the design work shall include the Inside Battery Limit (ISBL) and Outside Battery Limit (OSBL) of the facility.

ILF shall review each design stage appropriately, however, such review shall be done in milestones and not based on of available documentation. The following stages of review shall apply;

Front End Engineering Design

- Review of Basis of Design, process simulations, P&IDs, overall plant layouts and overall utility block diagrams (Electrical, Instrumentation, Communication etc ,

- Review of complete IFA packages based on agreed List of Deliverables

Detail Engineering Design

- Review IFR Packages based on agreed List of Deliverables

- Review IFA Packages / Procurement Packages based on agreed List of Deliverables

- Review IFC Packages / Procurement Packages based on agreed List of Deliverables

NOTE:

ILF shall treat the main process plant as a black box and verify only the expected inlet and outlet gas conditions.

ILF assumes that the design effort shall be robust and adequate to execute all aspects of the facility. The Consultant shall:

- Review contractor(s) Engineering Design activities; including design calculations, drawings, specifications, purchase orders, operating and maintenance manuals.

- Review Design/Engineering deliverables and to recommend to the client for approval.

- To provide professional advice to the client on design related issues.

- Lead and organize the safety review sessions such as HAZID, HAZOP and Constructability on all design deliverables. A third-party facilitator shall be provided via contract with Client for these reviews.

- Review the reports from activities including detailed surveys, detailed site investigations and other investigations necessary for the preparation of the detailed designs and drawings.

- Reviewing works and supporting activities during the surveys, site investigations and other investigations as necessary for the preparation of the detailed designs and drawings.

- Monthly Certification of technical progress for work done by the construction contractor(s) for inclusion in the monthly certificates or towards issuance of a milestone/job completion certificate.

## Procurement Supervision

- To review vendor’s procurement plans (Equipment and Material) and as well for the General Construction Contractor to ensure they are realistic and adequate.

- Review of Factory Acceptance Test (FAT) report and other vendor inspections, as well as vendor documentation for compliance with project requirements.

- Coordinate, attend and review Factory Acceptance Tests and Inspection of major Equipment and Materials carried out at Manufacturers and/or Suppliers sites for all major items of Equipment and Materials (where required) to ensure that all inspection and tests are carried out to the required level.

- To monitor delivery status of material and equipment to site based on the vendor’s  Procurement Plans.

- Issuance of regular procurement status reports to the client based on agreed frequency throughout the procurement phase of the project.

- Preparation of an integrated implementation schedule for the project.

## Construction Monitoring

ILF shall monitor the construction activities and ensure adherence to construction execution plans with respect to planning, scheduling, progress measurement, reporting, and administrative services are being completed in a safe, efficient, and timely manner in accordance with the Project Contracts, Project HSE requirements, Project Budget and Project Schedule.

ILF shall carry out random checks and periodically request evidence with regard to being compliant with the applicable country’s regulatory requirements. The obtaining of such permits is not the responsibility of ILF, but that of the Construction Contractor. Prior to the signing of a Contract, the Construction Contractor shall provide to the Client in advance, evidence that they are qualified to operate and perform construction activities in Nigeria, throughout the Project execution period.

ILF shall monitor and ensure that the Construction Contractor provides all inspection and/or testing reports and other related documentation required during construction in accordance with Project Contract requirements.

ILF shall monitor the construction on site with respect to HSE, including, but not limited to:

- the organizing and implementing, safety and quality environmental awareness trainings for their workforce, as well as that of their subcontractors and suppliers, for the duration of the Project Work in accordance with the approved procedures; and

- The compliance with the Project HSE requirements with respect to the provision, transport, storage, conservation, operation, and maintenance of the construction equipment and tools.

ILF shall monitor compliance during construction on site with Project Contract requirements, with respect to quality assurance and quality management.

ILF shall develop for the Client’s approval, the construction quality assurance requirements framework for the Project Work. ILF shall monitor but shall not be responsible for the Construction Contractor’s material management and its being in accordance with the requirements contained in the Project Contracts. ILF shall inform the Client of any non-compliances, which are observed and monitor the remedying thereof.

ILF shall coordinate with the Client, the Client’s participation in the Final Acceptance activities related to the Project Work and any inspections related thereto and connected with these activities.

Key tasks of the ILF shall include:

- Perform technical advisory work including periodic inspection of construction activities at site, review of construction progress reports and assessment of performance against agreed milestones.

- Certify achievement of milestones or work task prior to payment against relevant milestones.

- Review construction reports which set out, in reasonable detail, work carried out on the Project with commentary on likelihood of meeting the next milestone or any event which may delay the achievement, and issuance of monthly reports to the Client.

- Upon the request of Client, provide audits and reports to address specific queries.

- Review the construction schedule set out in the EPC Contract, compare with any revised schedules based on actual implementation.

- Provide to Client a description of any material disputes or proceedings (whether actual or threatened) relating to the Project during the previous month.

- Provide to Client a description of any accidents, emergencies or other events or circumstances which might have a material adverse impact on the construction schedule set out in the EPC Contract.

- Review and advise Client on any change orders or variations to the works under the Project Contracts and opine on the potential, or otherwise, for such variation to have a material impact on the Project.

- Obtain information on ongoing compliance with HSE/E&S requirements.

- Verify that required insurances are in place.

- Ensure that Client’s covenants and conditions are being met where applicable.

- Review all relevant insurances required to be in place.

- Participate in, and report to Client on, all Project testing events (sectional and overall), including NMDPRA testing/certification programs.

- Review and signoff on the EPC Completion certificate.

## Close-out Report

Prior to demobilizing of the TA, the team shall prepare a close-out report for the Client containing the following items:

- Diary of key events for the Project,

- Project status overview,

- Summary of outstanding work,

- Summary of key lessons learnt from Project implementation,

- Recommendations for further support,

- Operations handover status summary,

- Status of outstanding warranty items, and

- Operator execution plan for remainder of warranty period.

## Location

ILF (The Consultant) will setup a dedicated office within ILF’s existing facility in Lagos for the execution of the TA services (at no set-up cost). The Consultant’s Project Management Team would be based in this office and coordinate the activities of the project from its Lagos office.

The Engineering Design Management and Vetting team would be based in this office as well and coordinate all engineering efforts of the EPC contractor(s).

Office space shall be provided in individual EPC Contractor’s camp or site location.

## Key Resources

Table 2 – Key resource

| ID | Names | Role/Position |
| --- | --- | --- |
| 1 | Methana Bola / Obe Seyi | Project Manager |
| 2 | TBD | Project Engineer |
| 3 | Titilayo Giwa | Contracts Manager |
| 4 | QA / QC Engineer | Harrison Igbokweze |
| 5 | Willougby Evelyn | Document Control Specialist |
| 6 | Gobir AbdulMuminu | Engineering Manager |
| 7 | Olusuji Ogungbangbe | Package Specialist |
| 8 | Yewande Akinrinmade | Lead Process Engineer |
| 9 | Olumide-George Dawodu | Senior Process Designer |
| 10 | Samson Amila | Lead Mechanical Engineer |
| 11 | TBD | Senior Mechanical Engineer |
| 12 | Opeola Afolabi | Lead Civil & Structural Engineer |
| 13 | Abdulfatai Ogunleke | Senior Civil & Structural Engineer |
| 14 | Badejo Rahmon | Lead Pipeline Engineer |
| 15 | Olaleye Olusina | Civil & Structural Designer |
| 16 | Christopher Ugwu | Lead Instrument & Control Engineer |
| 17 | Charles Benwari | Lead Electrical Engineer |

Attachment 2 – Resume of key Personnel

### Manning Chart

Figure 3:Preliminary Execution Strategy .

Figure 4: Manning Chart.

## Safety on Site

Safe and secure working conditions are an essential prerequisite for Consultant’s activities on construction sites, camps and in the project area in general.

Should the situation or new discoveries or events on the ground provide reason for doubt concerning the security level on site or in country, Consultant reserves the right, in its own estimation and based on its own assessment, to suspend the affected part of the Services until doubt is cleared and an acceptable security level is re-established.

Client and Consultant will jointly ensure best efforts to establish confidence and share related information on the security level in a transparent and continuous manner.

# COMMERCIAL PROPOSAL

ILF shall conduct the above scope of services under the following commercial terms consisting of monthly visit (one (1) trip of five days each in every month) to the site location on commencement of construction:

## Labour Cost

|  |  | Labour Costs (USD | Total (USD) |
| --- | --- | --- | --- |
| Offer | : | $ 167,990.00 | $ 167,990.00 |

## Non Labour Costs

|  |  | Non-Labour Costs (USD – Transport and Accommodation (excluding flights) | Total (USD) |
| --- | --- | --- | --- |
| Budget Offer | : | $ 9,600.00 | $ 9,600.00 |

Note: Payment shall be made in Naira at the prevailing NAFEX exchange rate on the day of payment.

Notes:

- The above price is based on  Scope of Work specified in this proposal and exclusive of VAT.

- The above price ensures that minimum manning levels are always available and can be increased as required  based on project demands without recourse to additional sums within the contract duration.

- The above prices is limited to the number of and duration of site visits stated above. Additional site visits shall be reimbursed. The above prices do not contain any travel expenses and accommodation outside Nigeria.

- The above cost proposal is for information and budgeting purposes only. This service proposal is valid as a whole

- ILF expects that all Regulatory permits should have been secured by Client while EPC Contractor shall be responsible for all other permits/ licenses and as required for construction works.

- The price does not contain any cost for services to be provided by third party inspection services.

- Regular working time onsite during site surveys is 6 days per week, 10h per day; and

- Working time in Nigeria for Expat Staff is limited to 6 days per week, 10h per day.

## Payment Schedule

| Milestone | Description | Offer |
| --- | --- | --- |
| Mobilisation | 22.5% of Budget | $39,957.75 |
| Completion of FEED Review | 7.5% of Budget | $13,319.25 |
| Completion of DED Review | 10% of Budget | $17,759.00 |
| Submission of Report No. 7 | Fixed Monthly Payment | $10,655.40 |
| Submission of Report No. 8 | Fixed Monthly Payment | $10,655.40 |
| Submission of Report No. 9 | Fixed Monthly Payment | $10,655.40 |
| Submission of Report No. 10 | Fixed Monthly Payment | $10,655.40 |
| Submission of Report No. 11 | Fixed Monthly Payment | $10,655.40 |
| Submission of Report No. 12 | Fixed Monthly Payment | $10,655.40 |
| Submission of Report No. 13 | Fixed Monthly Payment | $10,655.40 |
| Submission of Report No. 14 | Fixed Monthly Payment | $10,655.40 |
| Submission of Report No. 15 | Fixed Monthly Payment | $10,655.40 |
| Submission of Report No. 16 | Fixed Monthly Payment | $10,655.40 |

## Reimbursable Rates

The services to be rendered by the Consultant outside of the above scope of work and the execution proposal shall be on a reimbursable basis exclusive of VAT based on previously agreed rates and weekly approved timesheets. The table below shows ILF standard rates:

| Cat. | Qualification | HOURLY RATES IN USD |  |
| --- | --- | --- | --- |
|  |  | ILF rates office works | ILF rates Works Nigeria |
|  |  | Nigeria (Expatriates) | (Local staff) |
| A | Project Manager / Senior Consultant / Construction Manager / Engineering Manager / Lead Engineers | 244 | 107 |
|  | Senior Engineers and Senior Construction Engineers | 195 | 75 |
| C | Engineers and Site Engineers | 154 | 54 |
| D | Technicians / Technical Draughtsman and qualified Assistance | 124 | 49 |
| E | Supporting Staff |  | 40 |

Table 3: Reimbursable Rate

General Notes:

- ILF-Rates for 2026 are valid until December 31st, 2026.

- Above rates apply for ILF-employees, agency personnel and consultants managed by ILF.

- Rates includes general overheads, management, administration, office services, office rent, furniture and office equipment, drafting and secretarial supplies, computer hardware, general and normal engineering software, local communications, normal in-house reprographic services (including up to 3 copies of draft and 3 copies of final documents), insurance, payroll burden, personnel taxes, holiday time, general office maintenance and profit.

- Regular working time in ILF Nigerian offices is 5 days per week, 8h per day.

- Regular working time onsite during site surveys is 6 days per week, 10h per day.

- Working time in Nigeria for Expat Staff is limited to 6 days per week, 10h per day.

- Rates are exclusive of VAT, which is to be reimbursed additionally where applicable.

- Payment shall be made within ten (10) calendar days after submission of each invoice.

## Non Labour Costs

For activities executed outside the scope of work defined herein, the non-labour costs such as travel, accommodation, messing, etc., if applicable, are to be invoiced at documented cost plus 15% mark-up.

This Service Proposal covers the license costs only for the following software: Operating system, Microsoft Word, Excel, PowerPoint, Outlook, AutoCAD, and the associated software listed herein.

If any special software is required, it will be acquired by ILF Engineers Nigeria at documented cost plus 15% mark-up or directly by client.

# ASSUMPTIONS AND EXCLUSIONS

ILF’s proposal does not include the Topographical Surveys, Soil Investigation and any environmental study;

Project and document language shall be English.

All Client provided documentation is available at the project kick-off and upon request if any other is required, no idle time waiting for receipt of documents is included here;

A qualified third party inspector for QA/QC activities is required for all testing and inspection services.

All Client’s provided documentation is in English language, no contingencies have been included in this proposal for translation. Translation of documents can be done upon request but it will be considered as a Variation Order to this Contract.

Access to the Terminal is granted, no idle time is considered due to strikes, accessibility problems due to terminal operator’s refusal to grant access, traffic conditions, local unrest, local communities, etc.;

Safety, Health and Environment protection while ILF Team is at site falls under the Client Responsibility including safety induction prior accessing the site. No resources are considered in this proposal from ILF for such.

Client shall provide third party inspection services for all quality inspections both at site and any fabrication locations. It is assumed that third party inspection (TPI) will be contracted directly by Client, in coordination and under the supervision of the Consultant.

The expected review time for documents submitted to Client is 5 working days. No contingencies are included in this proposal for a longer review time.

No procurement is envisaged and this priced proposal does not cover procurement. Any necessary procurement shall be approved by Client and made by ILF at cost plus 5%.

Client shall be responsible for the development of the gas supply pipeline and all other supporting infrastructure. Technical Advisory services related to these are not included in the current scope.

## Exclusions from Services

Please accept the following exclusions from our Services:

Purchase / supply of any equipment;

Any kind of procurement activities or procurement documents;

Any costs of the Company, licensors, authorities or third parties (incl. endorsement of documentation, personnel costs and applicable fees for permits, etc.) as well as their travel expenses and allowances;

Authority engineering;

Costs arising from participation of a third party are excluded from our services. Such costs are based on national principles and cannot be estimated yet (e.g. certified bodies, etc.);

Supply of any equipment (exempted from this are those facilities which are necessary for carrying out the services);

Local fees and charges that may be associated with the execution of the work on site;

Adaption of existing documentation in case of missing or incorrect data, conversion of the existing documentation into editable files (e.g. AutoCAD).

Any travel costs for Company’s personnel (e.g. visas, tickets, accommodation, meals, daily allowance, insurance, etc.)

# CONTRACT

Consultant proposes a FIDIC Client/Consultant Services Agreement as the Form of Agreement for the Project.  The following sections include proposed major terms to be included in the Particular Conditions clauses.

## Contractual Liability Cap

The Consultant would like to propose to cap the total aggregate of the contractual liability to a maximum value of 30% of the received remuneration on the Project.

## Project Language

The Consultant proposes that the Project language is English.

## Exclusion of Consequential Damages

The Consultant proposes exclusion of the consequential damages related to the Project. No compensation shall be payable by Consultant for indirect and/or consequential damage and loss of profit of the Client. This will be mutual for ILF and the Client

# CONCLUSION

We trust that our above proposal meets the Client’s approval. We remain at the Client’s disposal in case that any further information or clarifications are required. We are looking forward to an opportunity to work with you on this Project.

| Abiodun Oshodi |  |  |
| --- | --- | --- |
| Managing Director |  |  |
| ILF Engineers Nigeria Ltd. |  |  |

# ATTACHMENTS

Attachment 1 – Company Brochures

Attachment 2 – Resume of key Personnel