EPC ISSUES LIST

Location: Either change to Delta or Leave blank page 8.

Commissioning: Evans wants the 72hrs restated. Legal advice

Date of completion: addition of some terms for reasons for extension of time. Is it issued by owner or contractor? Legal advice

Review days: PCC requires 3 days, Owners engineer- ILF needs 5 working days. The Review period should be 5 working days.

Substantial completion, final completion   are outlined in section 11

Section 2.2 (b): The issue raised by evans should be ignored as the key personnel can be a factory manager who ensures all product are made to standard since PCC are the OEM for the contract.

Section 2.3 (c): the timeline is clear. The Contractor must give the Owner a formal heads-up at least four weeks (28 days) before officially signing a contract with a "Major Subcontractor."to give the owner time to do due diligence. The Contractor shall remain fully liable and responsible for the Work of all Subcontractors employed by the contractor only . Agreeable.

Section 3.1 (a): Rejection of the deletion of the part in 3.1 (a). It should be reinstated.

3.2 (b): the deleted part to be restated.  “The clause states that "The Works" isn't just what is written on the page; it includes anything implied or necessary for the project to be stable, safe, and fully functional. It prevents a contractor from saying, "I didn't install the bolts because the contract only mentioned the steel beams." If the building needs bolts to stand up, the bolts are part of the deal.” It protects the Owner’s interest.

3.3 (f): the deleted part is subject to approve from management. It protects the Owner from wrong info/results give to the contractor.

3.4 (d): it is self-explanatory. The contractor shall obey all permits.

3.5 (b(ii)): Fencing is our responsibility. Only providing armed security to secure the outer perimeter is our responsibility. It’s PCC responsibility to provide internal security to safe guard their operations and manage the provided security.

3.5 (b(iii)): deletion accepted as fence and provision of guards are our responsibility.

3.8 (c): the deleted part to be reinstated. If the law changes and a new tax is introduced mid-project, the Contractor doesn't lose money because the Owner is the one on the hook for it.

3.12 (a): I suggest reinstating some part such as “The Contractor shall use all reasonable endeavours to co-ordinate these activities with those of other contractors to the extent (if any) specified in the Owner’s Requirements or as instructed by the Owner’s Representative”

3.16: the terms seem ok

3.17 (v): can be rephrased to contractor scope or facilities so it can be borne by the contractor.

4.3 (d): it is not vague. Should be restated. The reinstated part by evans to be reviewed.

4.5 : subject to legal advice but seems ok.

4.5 Custom clearing: legal review on evans handover inclusion, legal review on the deleted section

4.12: legal team to kindly advise. Evans raise an issue of arbitration.

5.2 (d): inclusion of additional term subject to legal review.

5.3 (c): legal advice on deleted part.

5.8 (a(iv-vi): legal advise on additional EOT and probably inclusion of custom clearing delay on the owner’s side

6.1 (b): legal advice

6.3 (b): legal advice

7.2 (c): PCC are seeking retention bond not money. They earlier asked for retention money instead of bond.

7.5 (b): evans comment to be ignored.

7.7: legal advice on the clause.

8.1 (b): addition ok

8.2 (a): legal advise. Recheck to reinstate the deleted part. Remove wear and tear

9.1 (a(iii)): review

9.3.3: legal advice

9.6 (a): legal advise on deleted section but ok with it. Review of the included terms. It does not favour the owner in terms of leverage. We reject the terms.

9.6 (f): legal advise on the deleted section. The contractor cannot be dictating too much.

11.8 (b &c): allocation of days

12.2 (b): the deleted part can be subject to legal advice

12.2 (c): restate the deleted part and reduce the year from 2 to 1.

12.4: the deleted section is ok

12.6: warranty on rotary equipment should be increased to 2 years

15.1 and 15.2 (d): conflicting timeline, to be addressed

15.2 (e): the term is ok.

15.3 (a): legal review

15.4 (F): Legal review on clause not added

15.7 (a): legal review on added items.

17.1 (b): legal review on the deleted part

21.1.1 (i) & 21.2: Subject to legal advice

21.2.4.1 (d): Subject to legal advice

21.2.5.1 (a): Subject to legal advice

21.2.9 and 21.2.10: Subject to legal advice

Schedule A-1:

- Process Unit: there need to be inclusion of measuring meter to measure the feed intake

- Civil (Process equipment area): The road leading to the LNG loading zone shall be a concrete road instead of a simple unpaved road

Schedule E: Contract Price and Payment Schedule: The section is blank, legal advice

Schedule F: Insurance Sizing Guidance (iv): legal advice