MEETING MINUTES

Meeting Title: EPC Contract Review Meeting

Date: 8/4/2026

Location: Google Meets

Attendees:

- Mr Elias

- Mr. Ademola

- Mrs Loila

- Engr Akintunde

- Engr Oladotun

- Engr Ayoade

1. Defect Liability Period (DLP)

- Engr Akintunde proposed extending the Defect Liability Period to 12 months instead of 6 months. (Found in Definition)

- Liola indicated that there should be pushback on the issuing bank to our advantage. (Found in Definition)

2. Scope of Work

- Loila emphasized that the entire scope of work should be clearly captured in the schedule. (Found in Section 3.1)

3. Spare Parts

- Ayoade suggested that the team should push back on the spare parts requirement. (Found in Section 3.9)

- Loila and Mr Elias recommended re-engaging ILF to:

  - Confirm the timeline for document review

  - Assess if this may lead to an extension in schedule

(Found in Section 3.3)

4. Payment Terms

- Loila and Mr Elias suggested that the clause stating “contract price exclusive of all taxes” should be removed. (Found in Section 3.8)

5. Training and Spare Parts Inclusion

- Mr Elias suggested that training and spare parts should be added to the scope. (Found in Section 3.10)

6. Retention

- Loila proposed using a retention sum instead of a retention bond. (Found in Section 9.5)

7. Clause 7.6

- Section 7.6 was revised to state that it remains valid until the project is accepted.

8. Site Security

- Engr. Akintunde raised concerns about security on site, emphasizing that:

  - Equipment security must be handled by PCCN not the owner

  - While site security should be the owner’s responsibility

(Found in Section 4.5)

9. Performance Bond

Ayoade stated that the performance bond should remain at 10%. (Found in Section 9.4.1)

10. Life Design

The team agreed to push back on the life design requirement to 20 years rather than 10. (Found in Section 12.6)

11. Document Review Timeline

- Mr. Elias proposed 15 days for document review rather than 3 days.

- Engr Akintunde proposed 30 days

(Found in Section 4.10)

12. Owner’s Default

The team agreed to review the Owner’s Default clause. (Found in Section 15)

13. Performance Liquidated Damages & Delay Liquidated Damages

Ayo suggested that the maximum Delay Liquidated Damages should be between 10% - 20% not 5%, and Performance Liquidated Damages should be between 10% - 15% not 5% (Found in Section 13.1 and 13.2)

14. Aggregate Cap

The aggregate cap reduction from 100% to 5% cannot be accepted (Found in Section 17.1)