ENGINEERING, PROCUREMENT

AND CONSTRUCTION AGREEMENT

for the

5 MMSCFD MINI-LIQUEFIED NATURAL GAS PROJECT

by and between

SOUTH ATLANTIC LNG WEST AFRICA LIMITED

as Owner

and

PEIYANG CHEMICAL EQUIPMENT CO. LTD.

as Contractor

Dated as of the _____ Day of _____________, 20___

— CONFIDENTIAL —

TABLE OF CONTENTS

1. DEFINITIONS	10

1.1  General Definitions	10

2. RELATIONSHIP OF OWNER, CONTRACTOR AND SUBCONTRACTORS	15

2.1  Status of Contractor	15

2.2  Key Personnel and Contractor’s Representative	15

2.3  Subcontractors	15

2.4  Contractor Acknowledgements	16

3. CONTRACTOR’S RESPONSIBILITIES	17

3.1  Scope of Work	17

3.2  Standard of Care	17

3.3  Design and Engineering	18

3.4  Compliance with Laws	18

3.5  HSE Plan and Security	18

3.6  Quality Assurance and Quality Control	18

3.7  Reports and Records	19

3.8  Taxes	19

3.9  Spare Parts	20

3.10  Training	20

3.11  Clean-Up	20

3.12  Cooperation with Others	20

3.13  Environmental Management	20

4. OWNER’S RESPONSIBILITIES	22

4.1  Payment	22

4.2  Site Access	22

4.3  Owner Permits	22

4.4  Feedstock	22

4.5  Security	22

4.6  Customs and Import Duties	22

4.7  Geotechnical and Environmental Surveys	22

4.8  Community Relations	23

4.9  Owner’s Representative	23

4.10  Review Obligations	23

4.11  Financing	23

5. COMMENCEMENT OF WORK AND PROJECT SCHEDULE	24

5.1  Effective Date and Notice to Proceed	24

5.2  Conditions Precedent to NTP	24

5.3  Project Schedule	24

5.4  Delay and Recovery Schedule	24

5.5  Acceleration	25

6. CHANGES AND FORCE MAJEURE	26

6.1  Change Orders Requested by Owner	26

6.2  Change Orders Requested by Contractor	26

6.3  Change Orders Required by Government	26

6.4  Changes Due to Contractor Errors	27

6.5  No Adjustment Except by Change Order	27

6.6  Timing Requirements	27

6.7  Records	27

6.8  Force Majeure	27

7. CONTRACT PRICE AND PAYMENT	28

7.1  Contract Price	28

7.2  Payment Milestones	29

7.3  Advance Payment	29

7.4  Final Payment	29

7.5  Payments Withheld	29

7.6  Payment Not Acceptance	30

7.7  Offset	30

8. TITLE AND RISK OF LOSS	31

8.1  Passing of Title	31

8.2  Risk of Loss	31

9. INSURANCE, PERFORMANCE SECURITY AND PARENT GUARANTEE	32

9.1  Contractor’s Insurance	32

9.2  Performance Security — General	32

9.3  Advance Payment Guarantee	33

9.3.1  Issuance and Amount	33

9.3.2  Progressive Reduction	33

9.3.3  Expiry	33

9.3.4  Owner’s Right to Draw	34

9.4  Performance Bond	34

9.4.1  Issuance and Amount	34

9.4.2  Validity Period	34

9.4.3  Transition to Retention Bond	34

9.4.4  Owner’s Right to Draw	34

9.5  Retention Bond	35

9.5.1  Issuance and Amount	35

9.5.2  Retention Bond Delivery	35

9.5.3  Validity Period	35

9.5.4  Owner’s Right to Draw	35

9.6  General Provisions Applicable to All Guarantees	36

9.7  Owner’s Insurance	36

10. OWNERSHIP OF DOCUMENTATION AND INTELLECTUAL PROPERTY	37

10.1  Work Product	37

10.2  Contractor’s Pre-Existing IP	37

10.3  Documentation Deliverables	37

11. COMPLETION	38

11.1  Ready for Start-Up (RFSU)	38

11.2  Substantial Completion	38

11.3  Performance Test	38

11.4  Punchlist	39

11.5  Final Completion	39

11.6  Consequences of Failure to Achieve Substantial Completion	39

11.7  Owner’s Right to Use	40

12. WARRANTY AND CORRECTION OF WORK	41

12.1  Warranty	41

12.2  Defect Correction Period	41

12.3  Correction of Work Prior to Substantial Completion	41

12.4  Subcontractor Warranties	42

12.5  Exceptions to Warranty	42

12.6  Design Life Representation	42

12.7  Implied Warranties	42

13. LIQUIDATED DAMAGES	44

13.1  Delay Liquidated Damages	44

13.2  Performance Liquidated Damages	44

13.3  Liquidated Damages Not Penalty	44

13.4  Exclusive Remedy	44

13.5  Payment of Liquidated Damages	45

14. REPRESENTATIONS AND WARRANTIES OF THE PARTIES	46

14.1  Representations by Contractor	46

14.2  Representations by Owner	46

15. DEFAULT, TERMINATION AND SUSPENSION	48

15.1  Notice to Correct	48

15.2  Contractor Events of Default	48

15.3  Remedies Upon Contractor Default	48

15.3.1  Owner’s Step-In Rights	49

15.4  Owner Events of Default	50

15.5  Remedies Upon Owner Default	50

15.6  Termination for Convenience	50

15.7  Long Stop Date Termination	50

15.8  Termination Due to Extended Force Majeure	51

15.9  Suspension of Work	51

15.10  Effect of Termination	51

16. INDEMNIFICATION	52

16.1  Contractor’s Indemnification	52

16.2  Owner’s Indemnification	52

16.3  Indemnification Procedures	53

17. LIMITATION OF LIABILITY	54

17.1  Aggregate Cap	54

17.2  Consequential Damages	54

17.3  Caps on Liquidated Damages	54

17.4  Applicability	55

17.5  Time Limit on Claims	55

18. DISPUTE RESOLUTION	56

18.1  Negotiation	56

18.2  Mediation (Optional)	56

18.3  Arbitration	56

18.4  Continuation of Work	57

18.5  Escrow of Disputed Amounts	57

19. CONFIDENTIALITY	58

19.1  Obligations	58

19.2  Exceptions	58

19.3  Permitted Disclosures	58

19.4  Duration	58

20. MISCELLANEOUS PROVISIONS	59

20.1  Governing Law	59

20.2  Entire Agreement	59

20.3  Amendments	59

20.4  Severability	59

20.5  Assignment	59

20.6  Notices	59

20.7  No Waiver	60

20.8  Survival	60

20.9  Priority of Documents	60

20.10  Nigerian Content	60

20.11  Anti-Corruption	60

20.12  Language	61

20.13  Counterparts	61

20.14  Further Assurances	61

20.15  Successors and Assigns	61

20.16  Lender Requirements	61

20.17  Independence from Financing Arrangements	61

Schedule A-1: Scope of Work	63

Schedule A-2: Basis of Design	63

Schedule A-3: Performance Guarantee and Performance Test Procedures	64

Schedule B: Project Schedule and Key Milestones	64

Schedule C: Site Description	64

Schedule D: Key Personnel	64

Schedule E: Contract Price and Payment Schedule	65

Schedule F: Insurance Requirements	65

Schedule G: Form of Change Order	66

Schedule J: Forms of Completion Certificates	67

Schedule K: NCDMB / Nigerian Content Plan	67

RECITALS

THIS ENGINEERING, PROCUREMENT AND CONSTRUCTION AGREEMENT (hereinafter called the “Contract” or “Agreement”) is made and entered into this _____ day of _____________, 20___, by and between:

SOUTH ATLANTIC LNG WEST AFRICA LTD, a company incorporated under the Laws of the Federal Republic of Nigeria with RC NO 7865593, with its principal place of business office at H20, Onikoyi Lane, Parkview Estate, Ikoyi, Lagos, Nigeria (hereinafter referred to as the “Owner”, which expression shall, where the context so admits, include its successors-in-title and assigns) of the first part;

AND

PEIYANG CHEMICAL ENGINEERING SERVICE CORPORATION PTE LTD a company registered under the Laws of [Jurisdiction], whose principal place of business is No 17, Aroozoo Lane, Singapore, 539807 (hereinafter referred to as “PCCS” and also known as the “Contractor”, which expression shall, where the context so admits, include its successors-in-title and assigns) of the second part.

The Owner and the Contractor may collectively be referred to as the “Parties” and individually as a “Party.”

WHEREAS:

A. The Owner is desirous of constructing a ” 5MMSCFD Mini-LNG Processing Plant”(the “Project” or “Facility”) and has selected the Contractor to execute the engineering, procurement and construction of the Facility on a lump-sum turnkey basis;

B.  The Project shall be located at Epe/Ijebu Ode Toll Gate, Ogun State, Nigeria (the “Site”);

C.  The Contractor represents that it has the requisite experience, expertise, resources and capability to perform the Work in accordance with the terms hereof;

D.  The Parties wish to set forth the terms and conditions upon which the Contractor shall perform the Work and the Owner shall compensate the Contractor for the same;

NOW THEREFORE, in consideration of the mutual covenants and agreements herein contained, and for other good and valuable consideration, the receipt and sufficiency of which are hereby acknowledged, the Parties agree as follows:

# 1. DEFINITIONS

Unless the context otherwise requires, the following capitalized terms shall have the meanings assigned to them below when used in this Agreement:

## 1.1  General Definitions

“Acceptance Certificate” means the certificate issued by the Owner confirming that the Facility has achieved Substantial Completion in accordance with Article 11.

“Affiliate” means, with respect to any Person, any other Person that directly or indirectly controls, is controlled by, or is under common control with such Person.

“Aggregate Cap” has the meaning assigned in Section 17.1.

“Applicable Codes and Standards” means all applicable codes, standards and recommended practices of relevant Nigerian and international standards organizations as specified in Schedule A-2, as the same may be amended or supplemented from time to time.

“Applicable Law” means all constitutions, laws (including common law), treaties, statutes, orders, decrees, rules, injunctions, licenses, permits, approvals, agreements, regulations, codes and ordinances issued by any Governmental Authority, including judicial or administrative orders, consents, decrees and judgments, and all published directives, guidelines and governmental requirements which have the force of law, whether in effect as of the Effective Date or thereafter enacted, and in each case as amended.

“Approval” or “Approve” means a written communication from the Owner or Owner’s Representative to the Contractor confirming acceptance of a deliverable, work item, or other matter requiring Owner’s consent under this Agreement.

“Basis of Design” means the technical basis for the design and engineering of the Facility as set forth in Schedule A-2.

“Business Day” means any Day other than a Saturday, Sunday, or public holiday in the Federal Republic of Nigeria.

“Change Order” means a written document signed by both Parties authorizing a change in the Work, Contract Price, or Project Schedule in accordance with Article 6.

“Claim” means any and all judgments, claims, causes of action, demands, lawsuits, proceedings, governmental investigations or audits, losses, assessments, fines, penalties, administrative orders, obligations, costs, expenses, liabilities and damages (whether actual or consequential), including interest, penalties, reasonable attorney’s fees, disbursements and costs of investigations.

“Commissioning” means the process of testing and verifying the Facility’s systems and components to ensure that they are designed, installed, and operate in accordance with the requirements of this Agreement and the Basis of Design.

“Contract Price” means the total lump-sum amount payable by Owner to Contractor for the performance of the Work as set forth in Article 7, as may be adjusted by Change Orders in accordance with this Agreement.

“Contractor Group” means the Contractor, its Affiliates, Subcontractors, Sub-subcontractors, and their respective directors, officers, employees, agents and representatives.

“Contractor’s Representative” means the individual designated by the Contractor pursuant to Section 2.2 to act on behalf of the Contractor for matters arising under this Agreement.

“Corrective Work” means the investigation, correction, repair, replacement, re-performance, or removal of Defective Work.

“Day” means a calendar day.

“Defect” means any deficiency in the Work, including any part thereof, that does not conform to the Warranty or any other requirement of this Agreement.

“Defect Correction Period” means the period of twenty-four (24) months commencing on the date of Substantial Completion, during which Contractor is obligated to correct Defects at its own cost.

“Delay Liquidated Damages” has the meaning assigned in Section 13.1.

“Effective Date” means the date upon which both Parties have executed this Agreement.

“Equipment” means all machinery, equipment, apparatus, materials, articles and things of all kinds to be provided by or on behalf of the Contractor for incorporation into the Facility.

“Facility” means the [CNG Plant / LNG Facility / Mini LNG Plant] and all related works, infrastructure and ancillary systems to be designed, engineered, procured, constructed, installed, tested and commissioned by the Contractor pursuant to this Agreement.

“FEED” means Front-End Engineering Design.

“Final Completion” means the satisfaction by the Contractor of all requirements for Final Completion as set forth in Section 11.6.

“Force Majeure” has the meaning assigned in Section 6.8.

“Good Engineering and Construction Practice” or “GECP” means the practices, methods, standards, and procedures generally accepted and followed by prudent, diligent, skilled and experienced engineering, procurement and construction contractors performing work for facilities of the same or similar type, capacity, and complexity as the Facility, using equipment of the same or similar type.

“Governmental Authority” means any government, governmental administration, agency, instrumentality, political subdivision, court, commission, or other governmental authority of competent jurisdiction in the Federal Republic of Nigeria or any other applicable jurisdiction.

“Governmental Authorizations” means all licenses, permits, certificates, consents, approvals and other authorizations of, or issued by, any Governmental Authority required for the Project.

“Guaranteed Substantial Completion Date” means the date by which Substantial Completion is required to be achieved, as set forth in Schedule B, as the same may be extended by Change Orders issued in accordance with this Agreement.

“Issuing Bank” means the reputable international or Nigerian bank issuing any guarantee forming part of the Performance Security, as approved by the Owner.

“Key Personnel” means the individuals designated by the Contractor to fill the key positions identified in Schedule D.

“Long Stop Date” has the meaning assigned in Section 15.7.

“Advance Payment Guarantee” or “APG” means the irrevocable, unconditional, on-demand bank guarantee(s) to be provided by the Contractor in accordance with Section 9.3 to secure the Owner’s advance and milestone payments.

“Performance Bond” means the irrevocable, unconditional, on-demand bank guarantee to be provided by the Contractor in accordance with Section 9.4 to secure the Contractor’s performance during the construction phase.

“Performance Security” means collectively the Advance Payment Guarantee(s), Performance Bond and Retention Bond provided by the Contractor in accordance with Article 9.

“Retention Bond” means the irrevocable, unconditional, on-demand bank guarantee to be provided by the Contractor in accordance with Section 9.5 to secure the Contractor’s post-Substantial Completion obligations, including warranty and defect correction obligations.

“Major Subcontractor” means any Subcontractor whose subcontract value exceeds five percent (5%) of the Contract Price.

“Minimum Acceptance Criteria” means the minimum performance standards that the Facility must achieve for Substantial Completion, as specified in Schedule A-3.

“Month” means a calendar month.

“NCDMB” means the Nigerian Content Development and Monitoring Board established under the Nigerian Oil and Gas Industry Content Development Act 2010.

“Notice to Proceed” or “NTP” means the written notice issued by the Owner to the Contractor authorizing commencement of the Work in accordance with Section 5.2.

“Owner Group” means the Owner, its Affiliates, and their respective directors, officers, employees, agents, representatives and other contractors.

“Owner’s Representative” means the individual designated by the Owner pursuant to Section 4.9 to act on behalf of the Owner for matters arising under this Agreement.

“Performance Guarantee” means the guaranteed performance levels of the Facility as specified in Schedule A-3.

“Performance Liquidated Damages” has the meaning assigned in Section 13.2.

“Performance Test” means the tests to be conducted pursuant to Section 11.2 to demonstrate that the Facility meets the Performance Guarantee.

“Person” means any individual, partnership, limited liability company, joint venture, corporation, trust, unincorporated organization, Governmental Authority, or any other entity.

“Project Schedule” means the schedule for the performance of the Work, as set forth in Schedule B and as may be updated in accordance with this Agreement.

“Punchlist” means a list of minor items of Work that remain to be completed or corrected after Substantial Completion, none of which individually or in the aggregate materially affect the safe operation of the Facility.

“RFSU” or “Ready for Start-Up” means the stage at which the Facility has been mechanically completed and is ready for the introduction of feedstock for commissioning and start-up.

“Site” means the land and premises upon and under which the Facility is to be constructed, as more particularly described in Schedule C.

“Subcontractor” means any Person to whom the Contractor has subcontracted any part of the Work, or with whom the Contractor has entered into any agreement for the supply of goods, services, materials, or equipment in connection with the Work.

“Substantial Completion” means the achievement of all the requirements for Substantial Completion set forth in Section 11.2, including successful completion of the Performance Test and achievement of the Minimum Acceptance Criteria.

“Taxes” means any income, payroll, sales, use, excise, value-added, withholding, transfer and similar taxes, customs duties, fees and charges (including ad valorem taxes), including any interest or penalties attributable thereto, imposed by any Governmental Authority.

“Work” means all engineering, design, procurement, fabrication, supply, transportation, logistics, construction, installation, pre-commissioning, commissioning, start-up, performance testing, training and all other obligations to be performed by the Contractor under this Agreement, as more particularly described in Schedule A-1.

“Work Product” means all drawings, designs, specifications, calculations, reports, data, models, software (excluding pre-existing proprietary software), manuals, and other documents and materials prepared by or on behalf of the Contractor in connection with the Work.

# 2. RELATIONSHIP OF OWNER, CONTRACTOR AND SUBCONTRACTORS

## 2.1  Status of Contractor

The Contractor is an independent contractor performing the Work under this Agreement. Nothing in this Agreement shall create a joint venture, partnership, agency, or employment relationship between the Owner and the Contractor. The Contractor shall be solely responsible for the means, methods, techniques, sequences and procedures of construction and for safety precautions and programs in connection with the Work.

## 2.2  Key Personnel and Contractor’s Representative

(a) The Contractor shall designate a Contractor’s Representative who shall have full authority to act on behalf of the Contractor in all matters arising under this Agreement. The Contractor’s Representative shall be available at all reasonable times for consultation with the Owner.

(b) The Contractor shall assign the Key Personnel identified in Schedule D to the Project. The Contractor shall not remove or replace any Key Personnel without the prior written consent of the Owner, such consent not to be unreasonably withheld. If any Key Personnel become unavailable for reasons beyond the Contractor’s control, the Contractor shall promptly propose a replacement of equal or superior qualifications for the Owner’s approval.

(c) The Contractor shall provide and maintain an adequate organization chart for the Project, identifying all Key Personnel and their roles and responsibilities.

## 2.3  Subcontractors

(a) The Contractor may subcontract any portion of the Work to qualified Subcontractors. The Contractor shall select Subcontractors based on relevant criteria including experience, reputation, technical capability, and demonstrated success in comparable projects.

(b) The Contractor shall notify the Owner of all proposed Major Subcontractors prior to their engagement, including the name, scope of work and country of origin of each. The Contractor shall remain fully responsible for the Work of all Subcontractors and no subcontracting shall relieve the Contractor of any of its obligations under this Agreement.

(c) No subcontracting shall relieve the Contractor of any obligation or liability under this Agreement. The Contractor shall be fully responsible for the acts, defaults, and omissions of its Subcontractors as if they were the Contractor’s own.

(d) The Contractor shall ensure that all subcontracts contain provisions consistent with this Agreement that allow the Owner to exercise its rights hereunder, including provisions permitting assignment of such subcontracts to the Owner upon termination of this Agreement.

## 2.4  Contractor Acknowledgements

The Contractor acknowledges and agrees that: (a) it has reviewed and is familiar with the Project requirements, the Site conditions, and all other matters relevant to the performance of the Work; (b) it has satisfied itself as to the adequacy of the Contract Price; (c) it has made all necessary investigations and studies of conditions affecting the Work; and (d) it accepts full responsibility for the design, engineering, procurement, construction, and commissioning of the Facility in accordance with this Agreement.

# 3. CONTRACTOR’S RESPONSIBILITIES

## 3.1  Scope of Work

The Contractor shall perform the Work in accordance with this Agreement and all applicable Schedules, including Schedule A-1 (Scope of Work) and Schedule A-2 (Basis of Design). Without limiting the generality of the foregoing, the Contractor’s scope includes:

(a) Detailed engineering and design of the Facility;

(b) Procurement of all Equipment, materials and supplies required for the Facility;

(c) Fabrication and manufacturing of Equipment;

(d) Transportation, logistics and shipping of Equipment to the Site, including international shipping, import logistics to the nearest Nigerian port, and inland transportation from port to Site (unless otherwise allocated to Owner in Schedule A-1);

(e) Civil, structural, mechanical, electrical and instrumentation construction;

(f) Installation, pre-commissioning, commissioning and start-up of the Facility;

(g) Performance testing in accordance with Schedule A-3;

(h) Preparation and delivery of all as-built drawings, operation and maintenance manuals, and other documentation;

(i) Training of Owner’s operations and maintenance personnel; and

(j) All labour, supervision, services, materials, consumables, temporary works, equipment, tools, facilities and other items, whether expressly described or reasonably inferable from the Contract Documents, necessary to deliver a fully functional, safe, reliable and commercially operable Facility capable of achieving the Performance Guarantee on a continuous basis in accordance with this Agreement.

The Work is a lump-sum turnkey obligation. The Contractor acknowledges that the Contract Price includes all items necessary for completion of the Facility in accordance with this Agreement, whether or not expressly itemised in Schedule A-1, and no additional compensation shall be due except pursuant to a duly executed Change Order.

## 3.2  Standard of Care

The Contractor shall perform the Work in accordance with Good Engineering and Construction Practice, Applicable Law, Applicable Codes and Standards, and the requirements of all Governmental Authorizations applicable to the Work.

## 3.3  Design and Engineering

(a) The Contractor shall be responsible for the design and engineering of the Facility in accordance with the Basis of Design. All design documents, drawings and specifications shall be submitted to the Owner for review and comment. The Owner’s review shall not relieve the Contractor of its responsibility for the correctness and completeness of the design.

(b) The Owner shall review and provide comments on design submissions within ten (10) Business Days of receipt. If the Owner fails to provide comments within this period, the Contractor shall be entitled to an extension of the Project Schedule on a day-for-day basis to the extent such failure causes delay to the critical path, but such failure shall not constitute deemed approval of the submission.

## 3.4  Compliance with Laws

(a) The Contractor shall comply with all Applicable Laws, including without limitation all laws relating to health, safety, the environment, labour, immigration and tax.

(b) The Contractor shall comply with the Nigerian Oil and Gas Industry Content Development Act 2010 and all applicable NCDMB requirements, including minimum Nigerian content targets for the Project.

(c) The Contractor shall be responsible for obtaining and maintaining all Governmental Authorizations required for the performance of the Work by the Contractor (the “Contractor Permits”), at its own cost and expense.

## 3.5  HSE Plan and Security

(a) The Contractor shall develop and implement a comprehensive Health, Safety and Environment (HSE) plan for the Work, consistent with Good Engineering and Construction Practice and Applicable Law. The HSE plan shall be submitted to the Owner for review and approval prior to commencement of construction activities at the Site.

(b) The Contractor shall cooperate with the Owner’s security arrangements for the Site. The Owner shall be responsible for the overall security of the Site, including engagement of any required security forces.

## 3.6  Quality Assurance and Quality Control

The Contractor shall establish and maintain a quality assurance and quality control (QA/QC) program for the Work, including inspection and testing of Equipment and materials. The QA/QC program shall be consistent with Good Engineering and Construction Practice and shall be submitted to the Owner for review. The Owner shall have the right to witness any inspection or test upon reasonable notice.

## 3.7  Reports and Records

(a) The Contractor shall provide the Owner with weekly progress reports in a format acceptable to the Owner, including: (i) progress against the Project Schedule; (ii) Equipment procurement status; (iii) manpower and resource deployment; (iv) HSE statistics; (v) quality control results; (vi) updated cost reporting; and (vii) issues, risks and proposed mitigation measures.

(b) The Contractor shall maintain complete and accurate books and records relating to the Work. The Owner and its authorized representatives shall have the right to audit and inspect such books and records upon reasonable notice during the term of this Agreement and for a period of [three (3)] years following Final Completion.

## 3.8  Taxes

(a) The Contractor shall be responsible for all Taxes arising from or relating to the performance of the Work by the Contractor, its Subcontractors and their respective personnel, including but not limited to: corporate income tax, companies income tax, value-added tax (VAT), withholding tax on payments to Subcontractors, payroll taxes, personal income tax of the Contractor’s employees, education tax, and any state or local government levies.

(b) The Owner shall be responsible for: (i) customs duties, import levies, and port charges on Equipment imported for the Project (unless transportation and import logistics are allocated to the Contractor in Schedule A-1); (ii) any applicable duty exemptions, temporary importation permits, or tax incentives obtained by the Owner for the Project; and (iii) withholding tax on payments made to the Contractor under this Agreement to the extent required by Nigerian tax law, in which case the Owner shall provide the Contractor with evidence of such withholding and remittance to the relevant tax authority.

(c) The Contract Price is deemed to be inclusive of all Taxes for which the Contractor is responsible. The Contractor shall not be entitled to any adjustment of the Contract Price on account of Taxes in existence as of the Effective Date. If any new Tax is enacted after the Effective Date, or if the rate of an existing Tax is increased after the Effective Date, and such new or increased Tax directly affects the cost of the Work, the Contractor shall be entitled to a Change Order to the extent of the demonstrated impact.

(d) Each Party shall cooperate with the other in connection with any Tax matters, including the provision of documentation necessary for claiming tax exemptions, incentives or credits applicable to the Project.

## 3.9  Spare Parts

The Contractor shall provide commissioning spare parts and an initial set of recommended operating spare parts as specified in Schedule A-1. The Contractor shall also provide a recommended spare parts list sufficient for [two (2)] years of normal operation.

## 3.10  Training

The Contractor shall develop and deliver a comprehensive training program for the Owner’s operations and maintenance personnel. The training program shall include both classroom instruction and hands-on training at the Site during commissioning, and shall be completed prior to Substantial Completion. Details of the training program shall be as specified in Schedule A-1.

## 3.11  Clean-Up

The Contractor shall at all times keep the Site and adjacent areas free from unnecessary accumulation of waste materials and debris. Upon completion of the Work, the Contractor shall remove all temporary facilities, construction equipment, and waste materials from the Site, leaving the Site in a clean and safe condition.

## 3.12  Cooperation with Others

The Contractor shall cooperate with other contractors or service providers engaged by the Owner at the Site, and shall coordinate its Work so as not to unreasonably interfere with the work of others. The Contractor shall promptly notify the Owner of any actual or anticipated interference.

## 3.13  Environmental Management

(a) The Contractor shall be responsible for the proper handling, storage, transportation and disposal of all hazardous materials, chemicals, fuels, lubricants and waste generated by the Contractor or its Subcontractors in connection with the Work, in accordance with Applicable Law (including NESREA regulations and applicable NMDPRA guidelines).

(b) The Contractor shall be liable for and shall promptly remediate at its own cost any spills, leaks, discharges or releases of hazardous substances, pollutants or contaminants caused by the Contractor or its Subcontractors during the performance of the Work.

(c) The Contractor shall maintain a waste management plan and shall not dispose of any waste, chemicals or hazardous materials on the Site or at any location other than a licensed and approved disposal facility.

(d) This Section 3.13 shall not apply to pre-existing contamination present at the Site prior to the Contractor’s mobilisation, responsibility for which remains with the Owner pursuant to Section 16.2(c).

# 4. OWNER’S RESPONSIBILITIES

## 4.1  Payment

The Owner shall make all payments to the Contractor in accordance with Article 7.

## 4.2  Site Access

The Owner shall provide the Contractor with access to the Site in a condition suitable for the commencement and performance of the Work, in accordance with the Project Schedule. The Owner shall be responsible for: (a) providing adequate land for the Facility, including laydown areas; (b) fencing and site clearance; and (c) all matters relating to land acquisition, rights of way and easements.

## 4.3  Owner Permits

The Owner shall be responsible for obtaining and maintaining, at its own cost, all Governmental Authorizations required for the Project other than the Contractor Permits (the “Owner Permits”), including but not limited to environmental impact assessments, licenses to operate, approval-to-construct, and any other permits required by Nigerian regulatory authorities (NUPRC, NMDPRA, NESREA, State Government, etc.).

## 4.4  Feedstock

The Owner shall be responsible for procuring and supplying feedstock (natural gas or other applicable feedstock) to the Facility in quantities and at the pressure, temperature and quality specifications required for commissioning, performance testing and commercial operation, as set forth in Schedule A-2.

## 4.5  Security

The Owner shall establish and maintain appropriate security measures for the Site, including engagement of private security and coordination with relevant government security agencies as required. The security plan shall be developed in consultation with the Contractor and shall comply with all requirements of the Project insurers.

## 4.6  Customs and Import Duties

Unless otherwise allocated in Schedule A-1, the Owner shall be responsible for: (a) customs duties, import levies and clearance charges at Nigerian ports; and (b) all temporary importation permits and duty exemptions applicable to the Project.

## 4.7  Geotechnical and Environmental Surveys

The Owner shall be responsible for conducting and providing the Contractor with geotechnical, topographical and environmental survey data for the Site prior to the issuance of NTP. The Contractor shall be entitled to rely on such data, except to the extent that inaccuracies or discrepancies were reasonably discoverable by an experienced contractor exercising Good Engineering and Construction Practice through normal site inspection and verification activities. Any Change Orders resulting from materially different conditions discovered after NTP that were not ascertainable from such data (and were not reasonably discoverable as aforesaid) shall be processed in accordance with Article 6.

## 4.8  Community Relations

The Owner shall be responsible for community relations and stakeholder engagement in the area surrounding the Site, including negotiation of community development agreements and management of community-related risks.

## 4.9  Owner’s Representative

The Owner shall designate an Owner’s Representative who shall have full authority to act on behalf of the Owner in all matters arising under this Agreement. The Owner’s Representative shall be available at all reasonable times for consultation, document review, approvals and decision-making.

## 4.10  Review Obligations

The Owner shall review and, if found acceptable, approve all documents, drawings and deliverables submitted by the Contractor within the time periods specified in this Agreement. Where no specific period is stated, the Owner shall respond within ten (10) Business Days. Failure to respond within the applicable period shall not constitute deemed approval, but shall entitle the Contractor to an extension of time to the extent such failure causes delay to the critical path.

## 4.11  Financing

The Owner shall take all actions necessary to secure and maintain adequate financing to meet its payment obligations under this Agreement. The Owner shall provide reasonable evidence of available financing upon request by the Contractor.

# 5. COMMENCEMENT OF WORK AND PROJECT SCHEDULE

## 5.1  Effective Date and Notice to Proceed

(a) This Agreement shall become effective on the Effective Date. The Contractor shall not commence physical construction work at the Site until it has received the Notice to Proceed from the Owner.

(b) The Owner shall issue the Notice to Proceed within thirty (30) Days of the Effective Date, subject to the satisfaction of the conditions precedent set forth in Section 5.2.

## 5.2  Conditions Precedent to NTP

The obligation of the Owner to issue the Notice to Proceed is subject to the following conditions precedent:

(a) Receipt by the Owner of all required Owner Permits necessary for commencement of construction;

(b) Delivery by the Contractor of the Performance Bond and evidence of insurance in accordance with Article 9;

(c) The Site being accessible and available for the commencement of Work; and

(d) Such other conditions as may be specified in Schedule B.

## 5.3  Project Schedule

(a) The Contractor shall perform the Work in accordance with the Project Schedule set forth in Schedule B. The Project Schedule shall include all key milestones, including: engineering deliverables, procurement milestones, equipment delivery dates, construction milestones, commissioning dates, and the Guaranteed Substantial Completion Date.

(b) Time is of the essence with respect to the Contractor’s obligation to achieve Substantial Completion by the Guaranteed Substantial Completion Date.

(c) The Contractor shall submit detailed CPM (Critical Path Method) schedule updates on a monthly basis in a format acceptable to the Owner.

## 5.4  Delay and Recovery Schedule

(a) If the Contractor determines that the Work is falling behind the Project Schedule, the Contractor shall promptly notify the Owner and prepare a recovery schedule setting forth the measures to be taken to recover the delay, at no additional cost to the Owner (unless the delay is attributable to Owner-Caused Delay or Force Majeure).

(b) If the Owner reasonably determines that the Work is falling behind the Project Schedule, the Owner may request the Contractor to prepare and implement a recovery schedule.

## 5.5  Acceleration

The Owner may at any time request the Contractor to accelerate the Work. Any acceleration requested by the Owner shall be implemented through a Change Order in accordance with Article 6, and the Contractor shall be entitled to an adjustment of the Contract Price to reflect the reasonable additional costs of acceleration.

# 6. CHANGES AND FORCE MAJEURE

## 6.1  Change Orders Requested by Owner

(a) The Owner may at any time request a change in the Work by issuing a written Change Order Request to the Contractor. The Contractor shall, within [fifteen (15)] Business Days of receipt (or such longer period as may be reasonable given the complexity of the change), submit to the Owner a written proposal setting forth: (i) a description of the proposed change; (ii) the impact on the Contract Price (increase or decrease); (iii) the impact on the Project Schedule; and (iv) any other effects on the Work.

(b) Upon the Owner’s acceptance of the Contractor’s proposal, or upon agreement of the Parties as to the terms of the change, the Parties shall execute a Change Order incorporating the agreed terms. No change shall be implemented until a Change Order is executed, except where the Owner issues a written direction to proceed pending execution of a formal Change Order, in which case the Contractor shall proceed with the change and the terms shall be agreed subsequently.

(c) The cost of Owner-requested Change Orders shall be borne by the Owner.

## 6.2  Change Orders Requested by Contractor

(a) If the Contractor becomes aware of any condition, event or circumstance that it believes entitles it to a Change Order (including changes in Applicable Law, differing site conditions, or Owner-Caused Delay), the Contractor shall provide the Owner with written notice within [fifteen (15)] Days of becoming aware of such condition. Failure of the Contractor to provide notice within such period shall constitute a waiver of the Contractor’s entitlement to any adjustment of the Contract Price or Project Schedule arising from such event, unless the Contractor demonstrates that: (i) the Owner was not prejudiced by the late notice; and (ii) the Contractor provides notice within a further fifteen (15) Days thereafter.

(b) The Contractor shall submit a detailed Change Order Request within [thirty (30)] Days of the initial notice, setting forth: (i) the factual basis for the request; (ii) the contractual basis for the adjustment; (iii) the proposed adjustment to the Contract Price; (iv) the proposed adjustment to the Project Schedule; and (v) supporting documentation.

(c) The Owner shall respond to the Contractor’s Change Order Request within [fifteen (15)] Business Days. If the Parties cannot agree on the terms of a Change Order, the dispute shall be resolved in accordance with Article 18.

## 6.3  Change Orders Required by Government

If any action of a Governmental Authority enacted after the Effective Date requires a change to the Work that increases or decreases the scope, cost, or schedule, the Contractor shall be entitled to a Change Order reflecting the impact of such change. The cost impact shall be allocated to the Owner except to the extent the change arises from the Contractor’s failure to comply with Applicable Law in effect as of the Effective Date.

## 6.4  Changes Due to Contractor Errors

The Owner shall not be responsible for any increase in the Contract Price or extension of the Project Schedule resulting from changes that are necessary to correct errors, omissions, or deficiencies in the Contractor’s design, engineering, or construction of the Facility.

## 6.5  No Adjustment Except by Change Order

No adjustment shall be made to the Contract Price or the Project Schedule except by a duly executed Change Order or as otherwise expressly provided in this Agreement. The Contractor shall not be entitled to any additional compensation or extension of time unless a Change Order has been executed or is being processed in accordance with this Article 6.

## 6.6  Timing Requirements

The Contractor shall comply with the notice and timing requirements set forth in this Article 6 as a condition to its entitlement to any adjustment of the Contract Price or Project Schedule. The Parties agree that timely notice is essential to enable the Owner to mitigate the effects of any change or delay.

## 6.7  Records

The Contractor shall maintain detailed records of all Change Orders and Change Order Requests, including supporting documentation, cost analyses and schedule impact analyses, and shall make such records available to the Owner upon request.

## 6.8  Force Majeure

(a) “Force Majeure” means any event or circumstance that: (i) is beyond the reasonable control of the affected Party; (ii) could not have been reasonably anticipated or avoided; (iii) occurs without the negligence of the affected Party; and (iv) prevents the affected Party from performing its obligations under this Agreement. Force Majeure includes, but is not limited to: acts of God, fire, flood, drought, earthquake, windstorm, epidemic, pandemic; war, armed conflict, terrorism, civil commotion, blockade, embargo; strikes or labour disputes (other than those involving only the Contractor’s or its Subcontractors’ employees); and actions of a Governmental Authority that prevent performance (including changes in foreign trade or export policy affecting the shipment of Equipment to Nigeria).

(a-1) Notwithstanding the foregoing, the following shall not constitute Force Majeure: (i) supply chain disruptions, price increases, shortages of materials or equipment, or delays in delivery by vendors or suppliers, unless directly caused by a qualifying Force Majeure event described above; (ii) the financial hardship, insolvency, or cash flow difficulties of the Contractor, any Subcontractor, or any of their respective suppliers; (iii) the failure of any Subcontractor or supplier to perform its obligations, unless such failure is itself caused by a qualifying Force Majeure event; (iv) adverse weather conditions that are within the range of conditions reasonably foreseeable for the Site location and season; (v) labour shortages, unavailability of skilled personnel, or increases in labour costs; and (vi) changes in exchange rates, commodity prices, or market conditions.

(b) Neither Party shall be liable for any delay or failure in performance to the extent caused by Force Majeure, provided that the affected Party: (i) gives prompt written notice to the other Party of the Force Majeure event, including its nature, expected duration, and anticipated impact on the Work; (ii) uses reasonable efforts to mitigate the effects of the Force Majeure event; (iii) provides continuing updates on the status of the Force Majeure event; and (iv) gives prompt notice when the Force Majeure event has ceased.

(c) The Contractor shall be entitled to an extension of the Project Schedule on a day-for-day basis to the extent that a Force Majeure event causes delay to the critical path. Neither Party shall be entitled to an increase in the Contract Price on account of Force Majeure, except for reasonable demobilization and remobilization costs where the Force Majeure event requires suspension of Work for a continuous period exceeding [sixty (60)] Days.

(d) If a Force Majeure event continues for a period exceeding [one hundred eighty (180)] consecutive Days, either Party may terminate this Agreement by giving [thirty (30)] Days’ written notice to the other Party, and the consequences of such termination shall be as set forth in Section 15.8.

# 7. CONTRACT PRICE AND PAYMENT

## 7.1  Contract Price

(a) The Contract Price for the Work is [AMOUNT IN WORDS] ([AMOUNT IN FIGURES]) United States Dollars (USD), exclusive of any amounts to be adjusted by Change Orders in accordance with this Agreement.

(b) The Contract Price is a lump sum, fixed price, and includes all costs, expenses and profit of the Contractor necessary for the complete performance of the Work, except to the extent expressly stated otherwise in this Agreement.

(c) The Contract Price shall be denominated and payable in United States Dollars (USD), unless otherwise agreed in Schedule E.

## 7.2  Payment Milestones

(a) The Owner shall make payments to the Contractor in accordance with the payment milestone schedule set forth in Schedule E. Each milestone payment shall become due upon the Contractor’s achievement of the corresponding milestone and certification thereof by the Owner’s Representative.

(b) The Contractor shall submit an invoice with each payment request, together with supporting documentation demonstrating achievement of the relevant milestone. The Owner shall process and pay each properly supported invoice within thirty (30) Days of receipt.

(c) The Contractor shall deliver a Retention Bond in accordance with Section 9.5 no later than the date of Substantial Completion, to secure the Contractor's post-Substantial Completion obligations

## 7.3  Advance Payment

(a) Upon issuance of NTP and subject to the Contractor’s delivery of an Advance Payment Guarantee in accordance with Section 9.3, the Owner shall make an advance payment to the Contractor in accordance with the payment milestone schedule set forth in Schedule E. No advance or milestone payment shall be released until the Owner has received the corresponding APG.

(b) The advance payment shall be recovered by deduction from subsequent milestone payments on a pro-rata basis, and the APG shall be progressively reduced in accordance with Section 9.3.2 as recovery occurs.

## 7.4  Final Payment

Upon Final Completion and subject to the Contractor’s submission of all deliverables required for Final Completion, the Owner shall make the final payment to the Contractor, comprising the remaining balance of the Contract Price. The Contractor’s acceptance of final payment shall constitute a waiver of all claims by the Contractor against the Owner under this Agreement, except for claims previously made in writing and remaining unresolved.

## 7.5  Payments Withheld

(a) The Owner may withhold payment, in whole or in part, to the extent reasonably necessary to protect itself from loss on account of: (i) Defective Work not yet remedied; (ii) Claims or liens filed against the Work; (iii) the Contractor’s failure to make payments to Subcontractors when due; (iv) damage caused by the Contractor to the Owner or to other contractors at the Site; or (v) the Contractor’s failure to comply with any material obligation under this Agreement.

(b) Before withholding any payment, the Owner shall provide the Contractor with written notice specifying the grounds for withholding and the amount to be withheld. The Contractor shall have [ten (10)] Business Days to cure the matter or provide adequate assurance. Amounts withheld shall be released promptly upon the Contractor’s cure or resolution of the matter.

## 7.6  Payment Not Acceptance

No payment made by the Owner shall constitute acceptance of the Work or any part thereof, or relieve the Contractor of its obligations or liabilities under this Agreement.

## 7.7  Offset

The Owner shall have the right to offset against any amount payable to the Contractor any amount that is due and payable by the Contractor to the Owner under this Agreement, including Liquidated Damages, provided that the Owner gives the Contractor [ten (10)] Business Days’ prior written notice of its intention to exercise such right of offset.

# 8. TITLE AND RISK OF LOSS

## 8.1  Passing of Title

(a) Title to all Equipment, materials and Work Product shall pass to the Owner upon the earlier of: (i) delivery to the Site; (ii) payment by the Owner of the relevant milestone payment; or (iii) incorporation into the Facility.

(b) Notwithstanding the passing of title, the Contractor shall remain fully responsible for the care, custody and protection of the Equipment, materials and Work until Substantial Completion.

(c) The Contractor warrants that all Equipment and materials provided under this Agreement shall be free and clear of all liens, encumbrances and security interests at the time title passes to the Owner.

## 8.2  Risk of Loss

(a) The Contractor shall bear all risk of loss of, or damage to, the Work and all Equipment and materials delivered to the Site until Substantial Completion, except to the extent caused by the Owner, the Owner Group, or Force Majeure.

(b) Following Substantial Completion, risk of loss shall transfer to the Owner. The Contractor shall, however, remain responsible for any loss or damage to the Work to the extent caused by the Contractor during the Defect Correction Period while performing Corrective Work.

# 9. INSURANCE, PERFORMANCE SECURITY AND PARENT GUARANTEE

## 9.1  Contractor’s Insurance

(a) The Contractor shall obtain and maintain, at its own cost and expense, the insurance coverage set forth in Schedule F throughout the performance of the Work, with reputable insurers acceptable to the Owner. Such insurance shall include, at a minimum:

(i) Contractor’s All-Risk / Construction All-Risk Insurance;

(ii) Third Party Liability Insurance;

(iii) Workers’ Compensation and Employer’s Liability Insurance;

(iv) Professional Indemnity Insurance;

(v) Marine Cargo and Transit Insurance (for Equipment in transit);

(vi) Motor Vehicle Liability Insurance; and

(vii) Such other insurance as may be required by Applicable Law or specified in Schedule F.

(b) All policies shall name the Owner as an additional insured and/or loss payee, as applicable. All policies shall contain waivers of subrogation in favour of the Owner Group. The Contractor shall provide the Owner with certificates of insurance and copies of policies within fifteen (15) Days of the Effective Date and upon each renewal.

(c) The Contractor shall not cancel, materially alter, or allow to lapse any required insurance without giving the Owner at least [thirty (30)] Days’ prior written notice.

(d) The Contractor’s Professional Indemnity Insurance shall include a run-off period of not less than twelve (12) months following Final Completion, at no additional cost to the Owner.

## 9.2  Performance Security — General

The Contractor shall provide to the Owner the following performance security instruments (collectively, the “Performance Security”), each in the form of an irrevocable, unconditional, on-demand bank guarantee issued by a reputable international or Nigerian bank acceptable to the Owner (the “Issuing Bank”):

(i) Advance Payment Guarantee(s) (“APG”) in accordance with Section 9.3;

(ii) Performance Bond in accordance with Section 9.4; and

(iii) Retention Bond in accordance with Section 9.5.

Each guarantee shall be in the form set forth in Schedule I and shall be governed by the Uniform Rules for Demand Guarantees (URDG 758) published by the International Chamber of Commerce, or such other rules as the Parties may agree. The Contractor shall bear all costs, fees and charges associated with the issuance, maintenance, extension and amendment of all Performance Security instruments.

## 9.3  Advance Payment Guarantee

### 9.3.1  Issuance and Amount

(a) Prior to any advance or milestone payment by the Owner under Article 7, the Contractor shall deliver to the Owner an Advance Payment Guarantee in an amount equal to the advance or milestone payment to be received. No payment shall be due from the Owner until the corresponding APG has been received.

(b) Where multiple milestone payments are anticipated, the Contractor may issue a single APG covering the aggregate amount of all anticipated advance and milestone payments, or may issue separate APGs for each milestone payment, as agreed between the Parties.

### 9.3.2  Progressive Reduction

(a) The APG shall be progressively reduced (“amortised”) as the Contractor delivers Equipment to the Site, incorporates materials into the Work, and achieves verified progress milestones. The amount of each reduction shall correspond to the value of Work demonstrably performed or Equipment delivered against the relevant milestone payment, as certified by the Owner’s Representative.

(b) The Contractor shall submit a written request for reduction of the APG, accompanied by supporting documentation (including delivery receipts, installation certificates or progress verification reports). The Owner shall, within [ten (10)] Business Days of receipt of a valid request, provide the Contractor with a written consent letter to the Issuing Bank authorising the reduction.

(c) In no event shall the outstanding APG amount be reduced below the value of advance or milestone payments received by the Contractor less the verified value of Work performed and Equipment delivered to the Site.

### 9.3.3  Expiry

Each APG shall remain in effect until the earlier of: (a) full amortisation to zero in accordance with Section 9.3.2; or (b) Substantial Completion of the Facility. Any APG that has not been fully amortised by Substantial Completion shall remain in effect until the outstanding amount has been reconciled and either (i) the Contractor has delivered the corresponding Work, or (ii) the Owner has drawn on the APG for the undelivered balance.

### 9.3.4  Owner’s Right to Draw

The Owner may draw upon the APG if: (a) the Contractor fails to deliver Equipment or perform Work corresponding to a milestone payment within the timeframes specified in the Project Schedule, and such failure is not cured within [thirty (30)] Days of written notice; (b) a Contractor Event of Default occurs; or (c) this Agreement is terminated (for any reason other than Owner default or termination for convenience by the Owner) and the Contractor has received payments in excess of the verified value of Work performed.

## 9.4  Performance Bond

### 9.4.1  Issuance and Amount

(a) Within fifteen (15) Days of the Effective Date (and as a condition precedent to the issuance of NTP), the Contractor shall deliver to the Owner a Performance Bond in the amount of ten percent (10%) of the Contract Price.

(b) The Performance Bond shall guarantee the Contractor’s due and faithful performance of all of its obligations under this Agreement during the construction phase, including but not limited to: achieving Mechanical Completion; completing all commissioning activities; passing the Performance Test; and achieving Substantial Completion by the Guaranteed Substantial Completion Date.

### 9.4.2  Validity Period

The Performance Bond shall remain in full force and effect from the date of issuance until [twenty-eight (28)] Days after the date of Substantial Completion (the “Performance Bond Expiry Date”). If Substantial Completion is delayed beyond the Guaranteed Substantial Completion Date, the Contractor shall, at its own cost, procure an extension of the Performance Bond to cover the period of delay. The Contractor shall deliver evidence of such extension to the Owner not later than [thirty (30)] Days before the scheduled expiry of the Performance Bond.

### 9.4.3  Transition to Retention Bond

The Performance Bond shall not expire until the Owner has received the Retention Bond in accordance with Section 9.5. If the Contractor fails to deliver the Retention Bond by Substantial Completion, the Performance Bond shall be automatically extended (or the Contractor shall procure its extension) until the Retention Bond is received by the Owner.

### 9.4.4  Owner’s Right to Draw

The Owner may draw upon the Performance Bond if: (a) the Contractor fails to achieve Substantial Completion by the Guaranteed Substantial Completion Date and Delay Liquidated Damages are payable but unpaid; (b) a Contractor Event of Default occurs; (c) this Agreement is terminated for Contractor default; (d) the Contractor fails to perform Corrective Work required prior to Substantial Completion; or (e) any other amount becomes due from the Contractor to the Owner under this Agreement and remains unpaid after [fifteen (15)] Days’ written notice.

## 9.5  Retention Bond

### 9.5.1  Issuance and Amount

(a) No later than the date of Substantial Completion, the Contractor shall deliver to the Owner a Retention Bond in the amount of five percent (5%) of the Contract Price.

(b) The Retention Bond shall guarantee the Contractor’s due and faithful performance of all post-Substantial Completion obligations under this Agreement, including: correction of all Defects during the Defect Correction Period; completion of all Punchlist items; compliance with Warranty obligations under Article 12; and payment of any Performance Liquidated Damages.

### 9.5.2  Retention Bond Delivery

(a) The Retention Bond shall serve as the form of post-Substantial Completion security under this Agreement.

(b) Delivery of the Retention Bond is a mandatory condition of Substantial Completion. If the Contractor fails to deliver the Retention Bond by the date of Substantial Completion, the Owner shall not be obligated to issue the Substantial Completion Certificate until such delivery is made.

### 9.5.3  Validity Period

The Retention Bond shall remain in full force and effect until [twenty-eight (28)] Days after the later of: (a) Final Completion; and (b) expiry of the Defect Correction Period (including any extensions pursuant to Section 12.2(c)). If the Defect Correction Period is extended in respect of any repaired or replaced item, the Contractor shall procure a corresponding extension of the Retention Bond at its own cost.

### 9.5.4  Owner’s Right to Draw

The Owner may draw upon the Retention Bond if: (a) the Contractor fails to perform Corrective Work during the Defect Correction Period within the timeframes specified in Article 12; (b) the Contractor fails to complete Punchlist items within the period specified in Section 11.4; (c) Performance Liquidated Damages are payable but unpaid; (d) any other amount becomes due from the Contractor to the Owner in respect of post-Substantial Completion obligations and remains unpaid after [fifteen (15)] Days’ written notice; or (e) a Contractor Event of Default occurs during the Defect Correction Period.

## 9.6  General Provisions Applicable to All Guarantees

(a) Each guarantee forming part of the Performance Security shall be irrevocable, unconditional and payable on first written demand by the Owner without the need for the Owner to prove or demonstrate the underlying breach or default.

(b) If the Issuing Bank ceases to be acceptable to the Owner (including by reason of a downgrade in credit rating below investment grade), the Contractor shall, within [thirty (30)] Days of the Owner’s written request, procure a replacement guarantee from an alternative bank acceptable to the Owner. If the Contractor fails to deliver the replacement guarantee within such period, the Owner may draw on the existing guarantee and hold the proceeds as cash security.

(c) The Contractor shall ensure that each guarantee is extended, renewed or replaced as necessary to maintain continuous coverage for the full validity period. The Contractor shall deliver evidence of extension or renewal to the Owner not later than [thirty (30)] Days before the scheduled expiry of any guarantee.

(d) The Owner shall promptly return each guarantee to the Contractor (or provide a written release to the Issuing Bank) upon expiry of the relevant validity period, provided that no outstanding claims exist under such guarantee and all corresponding obligations of the Contractor have been satisfied.

(e) If the Owner draws on any guarantee, the Contractor shall, within [thirty (30)] Days, restore the guarantee to its original amount (or the then-applicable required amount) by delivering a replacement or top-up guarantee. Failure to restore the guarantee shall constitute a Contractor Event of Default.

(f) The Owner’s right to make demand under any Performance Security shall not be conditioned upon prior adjudication, arbitration or court determination of breach, and shall not require the Owner to demonstrate actual loss. The Contractor shall not seek or obtain any injunction, court order or other interim measure to prevent or delay the Owner from making a demand under any guarantee. Any dispute as to whether a demand was properly made shall be resolved after payment by the Issuing Bank, without prejudice to the Contractor’s right to seek recovery through the dispute resolution mechanism in Article 18.

## 9.7  Owner’s Insurance

The Owner shall obtain and maintain, at its own cost, any insurance required for the Owner’s own operations and property at or near the Site, as specified in Schedule F. Such insurance may include, at the Owner’s discretion, Delay in Start-Up (DSU) insurance.

# 10. OWNERSHIP OF DOCUMENTATION AND INTELLECTUAL PROPERTY

## 10.1  Work Product

(a) All Work Product developed by the Contractor specifically for the Project shall become the property of the Owner upon creation. The Contractor hereby assigns to the Owner all right, title and interest in and to such Work Product.

(b) The Owner shall have an irrevocable, perpetual, royalty-free license to use, copy, modify and distribute all Work Product for the purposes of operating, maintaining, modifying, repairing, expanding or decommissioning the Facility.

## 10.2  Contractor’s Pre-Existing IP

(a) The Contractor retains all right, title and interest in its pre-existing intellectual property, including proprietary software, processes, methodologies and know-how (“Contractor Background IP”).

(b) To the extent any Contractor Background IP is incorporated into or necessary for the use of the Facility, the Contractor hereby grants to the Owner an irrevocable, perpetual, royalty-free, non-exclusive license to use such Contractor Background IP solely in connection with the operation, maintenance, modification, repair and expansion of the Facility.

## 10.3  Documentation Deliverables

The Contractor shall deliver to the Owner, no later than Substantial Completion (unless otherwise specified), all documentation required under this Agreement, including: (a) as-built drawings; (b) operation and maintenance manuals; (c) equipment data sheets; (d) vendor warranties and certificates; (e) material test reports; (f) spare parts catalogues; and (g) all other documentation specified in Schedule A-1.

# 11. COMPLETION

## 11.1  Ready for Start-Up (RFSU)

(a) The Contractor shall give the Owner at least sixty (60) Days prior written notice of the expected date of RFSU. At such time as RFSU is achieved, the Contractor shall issue an RFSU Completion Certificate certifying that all mechanical completion requirements have been satisfied and the Facility is ready for the introduction of feedstock for commissioning and start-up.

(b) The Owner shall review the RFSU Completion Certificate and either accept it or provide the Contractor with written comments within [five (5)] Business Days. Upon acceptance, the Owner shall arrange for the delivery of feedstock in accordance with Section 4.4.

## 11.2  Substantial Completion

Substantial Completion shall be deemed to have occurred when all of the following requirements have been satisfied:

(a) The Facility has been constructed, installed and commissioned in accordance with this Agreement;

(b) The Performance Test has been successfully completed and the Facility has demonstrated that it meets the Minimum Acceptance Criteria;

(c) All required Governmental Authorizations for operation of the Facility have been obtained (to the extent they are the responsibility of the Contractor);

(d) All required documentation has been delivered to the Owner, including as-built drawings and operation and maintenance manuals;

(e) The training program has been completed;

(f) The Punchlist has been agreed between the Parties; and

(g) The Contractor has delivered the Substantial Completion Certificate and the Owner has accepted it.

## 11.3  Performance Test

(a) The Performance Test shall be conducted in accordance with the procedures set forth in Schedule A-3. The Performance Test shall demonstrate that the Facility meets the Performance Guarantee under the conditions specified in Schedule A-3.

(b) If the Facility fails to achieve the Performance Guarantee during the Performance Test, the Contractor shall, at its own cost, make such modifications, adjustments and repairs as are necessary and shall repeat the Performance Test. The Contractor shall have three (3) opportunities to pass the Performance Test.

(c) If the Facility achieves the Minimum Acceptance Criteria but does not achieve the full Performance Guarantee, Substantial Completion may be declared subject to the payment of Performance Liquidated Damages in accordance with Article 13.

(d) If the Facility fails to achieve the Minimum Acceptance Criteria after three (3) Performance Test attempts, the Owner may, at its sole option: (i) reject the Facility and terminate this Agreement for Contractor default in accordance with Section 15.3; (ii) accept the Facility subject to agreed Performance Liquidated Damages (including damages beyond the formulae in Schedule A-3, as may be negotiated); or (iii) require the Contractor to undertake further remedial measures at its own cost within a timeframe specified by the Owner, failing which the Owner may exercise its rights under sub-paragraph (i) or (ii) above.

## 11.4  Punchlist

(a) Prior to Substantial Completion, the Parties shall jointly prepare a Punchlist of minor items remaining to be completed or corrected. No item shall be included on the Punchlist if it materially affects the safe operation of the Facility or its ability to meet the Minimum Acceptance Criteria.

(b) The Contractor shall complete all Punchlist items within ninety (90) Days after Substantial Completion (or such other period as may be agreed by the Parties).

## 11.5  Final Completion

Final Completion shall be deemed to have occurred when:

(a) All Punchlist items have been completed to the Owner’s reasonable satisfaction;

(b) All remaining deliverables and documentation have been provided;

(c) The Site has been cleaned up in accordance with Section 3.11;

(d) All Contractor equipment and temporary facilities have been removed from the Site; and

(e) The Contractor has submitted and the Owner has accepted the Final Completion Certificate.

## 11.6  Consequences of Failure to Achieve Substantial Completion

If the Contractor fails to achieve Substantial Completion by the Guaranteed Substantial Completion Date (as may be extended by Change Orders), the Contractor shall be liable for Delay Liquidated Damages in accordance with Article 13.

## 11.7  Owner’s Right to Use

Notwithstanding anything to the contrary, the Owner shall have the right to operate and use the Facility from and after Substantial Completion, and such operation and use shall not be deemed acceptance of any Defective Work or waiver of any of the Owner’s rights under this Agreement.

# 12. WARRANTY AND CORRECTION OF WORK

## 12.1  Warranty

(a) The Contractor warrants that:

(i) all Equipment shall be new (unless otherwise agreed in writing) and of good quality;

(ii) the Work shall be performed in accordance with Good Engineering and Construction Practice, Applicable Law, Applicable Codes and Standards, and the requirements of this Agreement;

(iii) the Facility shall meet the Performance Guarantee;

(iv) the Work shall be free from Defects in design, materials and workmanship;

(v) all Work Product and documentation shall conform to this Agreement; and

(vi) the Facility, when completed, shall be fit for its intended purpose as a LNG Plant capable of processing natural gas feedstock and producing products at the rates and specifications set forth in Schedule A-2 and Schedule A-3 (the “Fitness for Purpose Warranty”).

## 12.2  Defect Correction Period

(a) During the Defect Correction Period, the Contractor shall, at its own cost and expense, promptly investigate, correct, repair, replace or re-perform any Defective Work upon receiving written notice from the Owner (or upon the Contractor’s own discovery of a Defect).

(b) If a Defect is of such nature that it materially impairs the safe operation of the Facility or its ability to meet the Performance Guarantee, the Contractor shall commence corrective action within [forty-eight (48)] hours of notification and shall proceed with all due diligence to complete the correction.

(c) If any Equipment or portion of the Work is repaired or replaced during the Defect Correction Period, the Warranty for such repaired or replaced item shall be extended for a period of twelve (12) months from the date of repair or replacement, provided that the total Defect Correction Period shall not extend beyond thirty-six (36) months from the date of Substantial Completion. The expiration of the Defect Correction Period shall not limit or extinguish any claim for latent defects arising from fraud, wilful concealment, wilful misconduct or gross negligence of the Contractor.

## 12.3  Correction of Work Prior to Substantial Completion

Prior to Substantial Completion, the Contractor shall, at its own cost and at the earliest practicable time, correct any Work that does not conform to the requirements of this Agreement. The Owner shall have the right to inspect all Work at reasonable times, and the Contractor shall provide adequate access for such inspections.

## 12.4  Subcontractor Warranties

The Contractor shall obtain warranties from all Subcontractors and Equipment suppliers that are no less favourable than the Warranty provided by the Contractor under this Agreement. All such warranties shall run to the benefit of the Contractor and shall be assignable to the Owner. Upon expiration of the Defect Correction Period, the Contractor shall assign all Subcontractor and supplier warranties to the Owner.

## 12.5  Exceptions to Warranty

The Warranty shall not apply to Defects to the extent caused by: (a) improper operation, maintenance, repair or alteration by the Owner or its personnel (other than operation in accordance with the Contractor’s operation and maintenance manuals); (b) normal wear and tear; (c) normal corrosion; (d) Force Majeure occurring after Substantial Completion; or (e) use of materials or feedstock not conforming to the specifications in this Agreement that were provided by the Owner.

## 12.6  Design Life Representation

The Contractor represents and warrants that the Facility has been designed and constructed for continuous operation in accordance with the Performance Guarantee for a minimum design life of twenty (20) years, subject to normal wear and tear and proper maintenance in accordance with the operation and maintenance manuals delivered under this Agreement. Nothing in this Section shall extend the Defect Correction Period, but this representation shall survive termination or expiration of this Agreement to the extent required to give effect to the Fitness for Purpose Warranty in Section 12.1(a)(vi) and the latent defects carve-out in Section 12.2(c).

## 12.7  Implied Warranties

EXCEPT AS EXPRESSLY SET FORTH IN THIS AGREEMENT (INCLUDING THE FITNESS FOR PURPOSE WARRANTY IN SECTION 12.1(a)(vi)), THE CONTRACTOR MAKES NO OTHER WARRANTIES, EXPRESS OR IMPLIED, INCLUDING ANY IMPLIED WARRANTIES OF MERCHANTABILITY. FOR THE AVOIDANCE OF DOUBT, THE EXPRESS WARRANTIES SET FORTH IN THIS ARTICLE 12 (INCLUDING THE FITNESS FOR PURPOSE WARRANTY) SHALL NOT BE LIMITED BY ANY IMPLIED WARRANTY EXCLUSION AND SHALL BE FULLY ENFORCEABLE IN ACCORDANCE WITH THEIR TERMS.

# 13. LIQUIDATED DAMAGES

## 13.1  Delay Liquidated Damages

(a) If the Contractor fails to achieve Substantial Completion by the Guaranteed Substantial Completion Date (as may be extended by Change Orders), the Contractor shall pay to the Owner Delay Liquidated Damages in the amount of 0.15% of the Contract Price per Day of delay (the “Delay LD Rate”), commencing on the Day after the Guaranteed Substantial Completion Date until the earlier of: (i) the date Substantial Completion is achieved; or (ii) the date the aggregate Delay Liquidated Damages reach the Delay LD Cap.

(b) The maximum aggregate liability of the Contractor for Delay Liquidated Damages shall be fifteen percent (15%) of the Contract Price (the “Delay LD Cap”).

## 13.2  Performance Liquidated Damages

(a) If the Facility achieves the Minimum Acceptance Criteria but fails to achieve the Performance Guarantee, the Contractor shall pay to the Owner Performance Liquidated Damages calculated in accordance with the formulae set forth in Schedule A-3.

(b) The maximum aggregate liability of the Contractor for Performance Liquidated Damages shall be ten percent (10%) of the Contract Price (the “Performance LD Cap”).

## 13.3  Liquidated Damages Not Penalty

The Parties agree that the Liquidated Damages specified in this Article 13 represent a genuine pre-estimate of the losses that would be suffered by the Owner in the event of delay or underperformance, and are not a penalty. The Parties have negotiated such amounts in good faith and agree that the actual damages would be difficult to ascertain.

## 13.4  Exclusive Remedy

(a) Delay Liquidated Damages shall constitute the Owner’s sole monetary remedy for delay in achieving Substantial Completion, provided that this limitation shall not restrict the Owner’s right to: (i) terminate this Agreement under Article 15 (including termination upon reaching the Long Stop Date under Section 15.7); (ii) draw on the Performance Security in accordance with Article 9; (iii) recover damages arising from fraud, wilful misconduct, or abandonment of the Work; or (iv) exercise any other non-monetary remedy available under this Agreement.

(b) Performance Liquidated Damages shall be the Owner’s sole and exclusive remedy for failure to achieve the Performance Guarantee, provided that the Facility has achieved the Minimum Acceptance Criteria.

## 13.5  Payment of Liquidated Damages

(a) Liquidated Damages shall be invoiced by the Owner and payable by the Contractor within [fifteen (15)] Days of receipt of invoice.

(b) If the Contractor fails to pay Liquidated Damages when due, the Owner may, at its option: (i) deduct the amount from any sum due to the Contractor; and/or (ii) draw upon the Performance Bond (for Delay Liquidated Damages accruing prior to Substantial Completion) or the Retention Bond (for Performance Liquidated Damages accruing after Substantial Completion) for such amount.

# 14. REPRESENTATIONS AND WARRANTIES OF THE PARTIES

## 14.1  Representations by Contractor

The Contractor represents and warrants to the Owner that, as of the Effective Date:

(a) It is duly organized, validly existing and in good standing under the laws of its jurisdiction of incorporation, and is duly qualified to do business in the Federal Republic of Nigeria;

(b) It has all necessary power and authority to execute, deliver and perform this Agreement;

(c) The execution, delivery and performance of this Agreement has been duly authorized by all requisite corporate action and does not conflict with any Applicable Law or any material contractual obligation;

(d) This Agreement constitutes a legal, valid and binding obligation enforceable against the Contractor in accordance with its terms;

(e) There is no pending or threatened litigation, arbitration or proceeding that could materially affect the Contractor’s ability to perform its obligations hereunder;

(f) It possesses or will obtain all intellectual property rights necessary for the performance of the Work without infringing the rights of any third party;

(g) It is not insolvent and is not the subject of any bankruptcy or insolvency proceedings; and

(h) It possesses the experience, qualifications, expertise and resources to perform the Work in accordance with this Agreement; and

(i) In entering into this Agreement and establishing the Contract Price, it has not relied upon any financial projections, revenue forecasts, economic models, rate-of-return analyses or similar financial information provided by or on behalf of the Owner, and it has independently satisfied itself as to the adequacy of the Contract Price.

## 14.2  Representations by Owner

The Owner represents and warrants to the Contractor that, as of the Effective Date:

(a) It is duly organized, validly existing and in good standing under the laws of the Federal Republic of Nigeria;

(b) It has all necessary power and authority to execute, deliver and perform this Agreement;

(c) The execution, delivery and performance of this Agreement has been duly authorized by all requisite corporate action and does not conflict with any Applicable Law or any material contractual obligation;

(d) This Agreement constitutes a legal, valid and binding obligation enforceable against the Owner in accordance with its terms;

(e) There is no pending or threatened litigation, arbitration or proceeding that could materially affect the Owner’s ability to perform its obligations hereunder; and

(f) It is not insolvent and is not the subject of any bankruptcy or insolvency proceedings.

# 15. DEFAULT, TERMINATION AND SUSPENSION

## 15.1  Notice to Correct

If the Contractor fails to carry out any obligation under this Agreement, the Owner may by written notice require the Contractor to make good the failure and to remedy it within a reasonable time specified in the notice (not being less than fourteen (14) Days). This notice shall specify the obligation that has not been performed and the remedial action required. Failure by the Contractor to comply with a Notice to Correct within the specified period shall constitute a Contractor Event of Default under Section 15.2.

## 15.2  Contractor Events of Default

Each of the following shall constitute a Contractor Event of Default:

(a) The Contractor becomes insolvent, bankrupt, or is the subject of proceedings for liquidation, winding-up or dissolution that are not dismissed within [sixty (60)] Days;

(b) Any material representation made by the Contractor in this Agreement is false or misleading in any material respect when made;

(c) The Contractor materially fails to perform its obligations under this Agreement and does not cure such failure within [thirty (30)] Days after receipt of written notice from the Owner (or such longer cure period as may be reasonable if the breach is not susceptible to cure within thirty (30) Days, provided the Contractor commences cure within such period and diligently pursues it);

(d) The aggregate Delay Liquidated Damages payable reach the Delay LD Cap; or

(e) The Contractor abandons or suspends the Work without proper justification for a continuous period exceeding [thirty (30)] Days.

## 15.3  Remedies Upon Contractor Default

Upon the occurrence and continuance of a Contractor Event of Default, the Owner may exercise any one or more of the following remedies concurrently or separately:

(a) Terminate this Agreement by giving [fifteen (15)] Days’ written notice to the Contractor;

(b) Draw upon any or all of the Performance Security (including the APG, Performance Bond and/or Retention Bond, as applicable) to satisfy any amounts due from the Contractor;

(c) Exercise any other remedies available under Applicable Law.

### 15.3.1  Owner’s Step-In Rights

(a) Upon termination for Contractor default, or where the Owner reasonably determines that the Contractor is unable or unwilling to complete the Work, the Owner shall have the right (but not the obligation) to step in and take over all or any part of the Work (“Step-In Rights”). The Owner may complete the Work itself or engage one or more replacement contractors to complete the Work.

(b) To give effect to the Step-In Rights, upon termination for Contractor default or exercise of Step-In Rights, the Contractor shall:

(i) Immediately cease all Work and vacate the Site in an orderly manner;

(ii) Deliver to the Owner all Work Product, including all drawings, designs, specifications, calculations, engineering data, vendor documentation, procurement records and all other documentation (whether in draft or final form) in the Contractor’s possession;

(iii) Assign to the Owner (without recourse to the Contractor), at the Owner’s election, any or all of the Contractor’s subcontracts, purchase orders, supply agreements and other agreements entered into in connection with the Work. The Contractor shall include in all subcontracts and purchase orders a provision permitting such assignment without the consent of the Subcontractor or supplier;

(iv) Grant the Owner an irrevocable, royalty-free licence to use all Contractor Background IP to the extent necessary to complete the Work, operate, maintain, modify, repair and expand the Facility;

(v) Deliver to the Owner all Equipment and materials (whether at the Site, in transit, or at the Contractor’s or Subcontractors’ premises) for which title has passed to the Owner or for which the Owner has made payment;

(vi) Provide reasonable cooperation and technical assistance (including making available relevant personnel for a transition period of up to [sixty (60)] Days) to enable the Owner or its replacement contractor to understand the status of the Work and continue the Work without undue disruption; and

(vii) Remove all Contractor-owned construction equipment, temporary facilities and debris from the Site within [thirty (30)] Days of termination (or such longer period as the Owner may reasonably permit).

(c) The incremental cost of completing the Work (being the total cost incurred by the Owner to complete the Work less the unpaid balance of the Contract Price) shall be borne by the Contractor. If such incremental cost exceeds the amounts recoverable under the Performance Security, the Contractor shall remain liable for the excess, subject to Article 17.

(d) The Owner shall not be required to make any further payments to the Contractor until the Work has been completed and the total cost of completion has been determined. If the total cost of completion (including all amounts drawn under the Performance Security) is less than the unpaid balance of the Contract Price, the Owner shall pay the difference to the Contractor.

## 15.4  Owner Events of Default

Each of the following shall constitute an Owner Event of Default:

(a) The Owner becomes insolvent, bankrupt, or is the subject of proceedings for liquidation, winding-up or dissolution that are not dismissed within [sixty (60)] Days;

(b) Any material representation made by the Owner in this Agreement is false or misleading in any material respect when made; or

(c) The Owner commits a material breach of its obligations under this Agreement and fails to cure such breach within a reasonable period after receipt of written notice from the Contractor specifying the breach in reasonable detail.

## 15.5  Remedies Upon Owner Default

Upon the occurrence and continuance of an Owner Event of Default, the Contractor may suspend or terminate this Agreement by giving reasonable written notice to the Owner, and may exercise any other remedies available under Applicable Law.

## 15.6  Termination for Convenience

(a) The Owner may terminate this Agreement for convenience at any time by giving [thirty (30)] Days’ written notice to the Contractor.

(b) Upon termination for convenience, the Owner shall pay to the Contractor: (i) the value of Work performed prior to the date of termination; (ii) the cost of materials and Equipment already ordered or delivered; (iii) reasonable demobilization costs; and (iv) a reasonable amount for loss of anticipated profit on the unperformed portion of the Work, not to exceed five percent (5%) of the value of the unperformed Work.

## 15.7  Long Stop Date Termination

(a) If Substantial Completion has not been achieved by the date falling one hundred (100) Days after the Guaranteed Substantial Completion Date (as may be extended by Change Orders) (the “Long Stop Date”), the Owner shall be entitled to terminate this Agreement by giving fifteen (15) Days’ written notice to the Contractor.

(b) Termination under this Section 15.7 shall be treated as termination for Contractor default under Section 15.3, and the Owner shall be entitled to exercise all remedies set forth therein (including drawing on the Performance Security and engaging a replacement contractor to complete the Work at the Contractor’s cost).

(c) For the avoidance of doubt, the Owner’s right to terminate under this Section 15.7 is in addition to (and not in substitution for) the Owner’s entitlement to Delay Liquidated Damages under Article 13 up to the Delay LD Cap.

## 15.8  Termination Due to Extended Force Majeure

If this Agreement is terminated due to an extended Force Majeure event in accordance with Section 6.8(d), the Owner shall pay to the Contractor the value of Work performed prior to the date of termination and the cost of materials and Equipment already ordered or delivered, but neither Party shall have any further liability to the other in connection with such termination.

## 15.9  Suspension of Work

(a) The Owner may at any time direct the Contractor to suspend all or part of the Work for a specified period. The Contractor shall comply with such direction and shall take all necessary measures to protect and preserve the Work during the period of suspension.

(b) If the suspension continues for more than [ninety (90)] consecutive Days and is not caused by a Contractor Event of Default, the Contractor may treat the suspension as a termination for convenience under Section 15.6.

(c) The Contractor shall be entitled to a Change Order for reasonable costs incurred as a direct result of the suspension (including standby costs and demobilization/remobilization costs) and an extension of the Project Schedule by the duration of the suspension, except where the suspension is caused by a Contractor Event of Default.

## 15.10  Effect of Termination

(a) Upon termination by either Party, title to all Work and Work Product completed as of the termination date shall vest in the Owner (to the extent title has not already passed), subject to the Owner’s payment obligations under the applicable termination provisions.

(b) Termination of this Agreement shall not relieve either Party of obligations that accrued prior to the termination date or of obligations expressly stated to survive termination.

# 16. INDEMNIFICATION

## 16.1  Contractor’s Indemnification

The Contractor shall defend, indemnify and hold harmless the Owner Group from and against any and all Claims, damages, losses, costs and expenses (including reasonable legal fees) arising out of or resulting from:

(a) The Contractor’s failure, or the failure of any member of the Contractor Group, to comply with Applicable Law;

(b) Bodily injury or death of any person, or damage to property of any third party, to the extent caused by the negligence, wilful misconduct, or breach of this Agreement by any member of the Contractor Group;

(c) Infringement of any patent, copyright, trademark, or other intellectual property right of any third party arising from the Work (excluding infringement arising from the Owner’s specifications or designs);

(d) Any liens or encumbrances placed on the Work, the Facility or the Site arising from the Contractor’s failure to make payments to Subcontractors or suppliers;

(e) Bodily injury or death of any member of the Contractor Group, regardless of cause, except to the extent caused by the gross negligence or wilful misconduct of the Owner Group; and

(f) Environmental contamination, pollution, spills, releases or discharges of hazardous substances caused by the Contractor or any member of the Contractor Group during the performance of the Work, including the costs of remediation, clean-up, monitoring, fines and penalties imposed by any Governmental Authority, and any third party claims arising therefrom (excluding pre-existing contamination at the Site for which the Owner is responsible under Section 16.2(c)).

## 16.2  Owner’s Indemnification

The Owner shall defend, indemnify and hold harmless the Contractor Group from and against any and all Claims, damages, losses, costs and expenses (including reasonable legal fees) arising out of or resulting from:

(a) The Owner’s failure to comply with Applicable Law;

(b) Bodily injury or death of any person, or damage to property of any third party, to the extent caused by the negligence, wilful misconduct, or breach of this Agreement by any member of the Owner Group;

(c) Pre-existing environmental contamination or hazardous materials at the Site that were present prior to the commencement of the Work; and

(d) Bodily injury or death of any member of the Owner Group, regardless of cause, except to the extent caused by the gross negligence or wilful misconduct of the Contractor Group.

## 16.3  Indemnification Procedures

A Party seeking indemnification shall promptly notify the indemnifying Party in writing of any Claim, and shall cooperate with the indemnifying Party in the defence thereof. The indemnifying Party shall have the right to control the defence and settlement of any such Claim, provided that the indemnified Party shall have the right to participate in such defence at its own expense. No settlement shall be entered into without the indemnified Party’s prior written consent, such consent not to be unreasonably withheld.

# 17. LIMITATION OF LIABILITY

## 17.1  Aggregate Cap

(a) Notwithstanding any other provision of this Agreement, the Contractor’s aggregate liability to the Owner under this Agreement, whether in contract, tort, strict liability, indemnity, or any other cause of action, shall not exceed one hundred percent (100%) of the Contract Price (the “Aggregate Cap”).

(b) The Aggregate Cap shall not apply to: (i) the Contractor’s indemnification obligations under Section 16.1(b) (personal injury/death), Section 16.1(c) (IP infringement), Section 16.1(d) (liens), Section 16.1(e) (Contractor Group injuries), and Section 16.1(f) (environmental contamination); (ii) liability arising from the Contractor’s fraud, gross negligence, or wilful misconduct; (iii) obligations under Article 8 (title and lien-free delivery); and (iv) proceeds of the Performance Security instruments or insurance policies required by this Agreement (the “Carve-Outs”).

## 17.2  Consequential Damages

NEITHER THE OWNER GROUP NOR THE CONTRACTOR GROUP SHALL BE LIABLE TO THE OTHER UNDER THIS AGREEMENT FOR ANY SPECIAL, INDIRECT, INCIDENTAL OR CONSEQUENTIAL DAMAGES, INCLUDING LOSS OF PROFITS, LOSS OF USE, LOSS OF OPPORTUNITY, LOSS OF REVENUE, LOSS OF FINANCING, LOSS OF GOODWILL, OR BUSINESS INTERRUPTION, REGARDLESS OF WHETHER SUCH DAMAGES ARE BASED ON CONTRACT, TORT, STRICT LIABILITY OR ANY OTHER THEORY; PROVIDED THAT THIS EXCLUSION SHALL NOT APPLY TO: (A) AMOUNTS ENCOMPASSED WITHIN LIQUIDATED DAMAGES; (B) THE CONTRACTOR’S INDEMNIFICATION OBLIGATIONS UNDER SECTION 16.1 WITH RESPECT TO THIRD PARTY CLAIMS; (C) LIABILITY ARISING FROM A PARTY’S FRAUD OR WILFUL MISCONDUCT; OR (D) LIABILITY ARISING FROM THE CONTRACTOR’S ABANDONMENT OF THE WORK.

## 17.3  Caps on Liquidated Damages

(a) The Contractor’s maximum liability for Delay Liquidated Damages shall be limited to the Delay LD Cap.

(b) The Contractor’s maximum liability for Performance Liquidated Damages shall be limited to the Performance LD Cap.

(c) The aggregate of Delay Liquidated Damages and Performance Liquidated Damages shall not exceed twenty percent (20%) of the Contract Price.

## 17.4  Applicability

THE WAIVERS, DISCLAIMERS, RELEASES, EXCLUSIONS, LIMITATIONS AND APPORTIONMENTS OF LIABILITY EXPRESSED IN THIS AGREEMENT SHALL APPLY EVEN IN THE EVENT OF FAULT, NEGLIGENCE, STRICT LIABILITY, BREACH OF CONTRACT OR OTHERWISE OF THE PARTY RELEASED OR WHOSE LIABILITY IS WAIVED, DISCLAIMED, LIMITED OR INDEMNIFIED, TO THE MAXIMUM EXTENT PERMITTED BY APPLICABLE LAW.

## 17.5  Time Limit on Claims

No claim shall be brought by either Party against the other Party under this Agreement after the expiration of [three (3)] years following Substantial Completion (or, in the case of claims relating to the Defect Correction Period, [three (3)] years following the expiration of the Defect Correction Period), except for claims relating to fraud, wilful misconduct, IP infringement, or personal injury.

# 18. DISPUTE RESOLUTION

## 18.1  Negotiation

(a) If any dispute or difference of any kind arises between the Parties in connection with or arising out of this Agreement (a “Dispute”), the Parties shall first attempt to resolve such Dispute through good faith negotiation between their respective project managers within [fifteen (15)] Business Days of written notice of the Dispute.

(b) If the Dispute cannot be resolved at the project manager level, either Party may escalate the Dispute by written notice to the senior management (CEO, Managing Director or equivalent) of the other Party. The senior management of both Parties shall meet (in person or by video conference) within [fifteen (15)] Business Days of such escalation and shall endeavour to resolve the Dispute.

## 18.2  Mediation (Optional)

If the Dispute is not resolved by negotiation within [thirty (30)] Days of the initial notice, either Party may propose that the Dispute be submitted to mediation under the rules of [the Lagos Court of Arbitration / Chartered Institute of Arbitrators (Nigeria Branch)]. Mediation shall be voluntary and non-binding.

## 18.3  Arbitration

(a) Any Dispute that is not resolved by negotiation (and, if applicable, mediation) within [sixty (60)] Days of the initial written notice shall be finally settled by arbitration.

(b) The arbitration shall be conducted in accordance with the Arbitration and Mediation Act 2023 of the Federal Republic of Nigeria and the rules of the [Lagos Court of Arbitration / Chartered Institute of Arbitrators, Nigeria Branch], as in effect at the time of the arbitration.

(c) The arbitration shall be conducted by [three (3)] arbitrators. Each Party shall appoint one arbitrator, and the two appointed arbitrators shall jointly appoint the third arbitrator, who shall serve as chairman. If the two arbitrators fail to agree on the third arbitrator within [fifteen (15)] Days, the appointing authority under the applicable rules shall make the appointment.

(d) The seat of the arbitration shall be [Lagos / Abuja], Nigeria.

(e) The language of the arbitration shall be English.

(f) The arbitral award shall be final and binding on the Parties and may be enforced in any court of competent jurisdiction.

(g) Each Party shall bear its own costs and legal fees in connection with the arbitration, and the costs of the arbitration (including arbitrator fees) shall be shared equally unless the tribunal orders otherwise.

## 18.4  Continuation of Work

The Contractor shall continue to perform the Work during the pendency of any Dispute, and the Owner shall continue to make undisputed payments in accordance with this Agreement, unless this Agreement is otherwise terminated.

## 18.5  Escrow of Disputed Amounts

If a Dispute relates to a payment obligation, the Owner may deposit the disputed amount into an interest-bearing escrow account pending resolution of the Dispute. Such deposit shall not constitute a default under this Agreement.

# 19. CONFIDENTIALITY

## 19.1  Obligations

Each Party shall keep confidential and shall not disclose to any third party (without the prior written consent of the other Party) any Confidential Information received from the other Party in connection with this Agreement. “Confidential Information” means all technical, commercial, financial or other information relating to the business, operations or affairs of the disclosing Party that is disclosed or made available to the receiving Party in connection with this Agreement, whether disclosed orally, in writing, electronically or by any other means.

## 19.2  Exceptions

The obligations in Section 19.1 shall not apply to information that: (a) is or becomes publicly available through no fault of the receiving Party; (b) was known to the receiving Party prior to disclosure; (c) is independently developed by the receiving Party without reference to the Confidential Information; (d) is received from a third party without restriction on disclosure; or (e) is required to be disclosed by Applicable Law, Governmental Authority, court order, or the rules of any relevant stock exchange, provided that the receiving Party gives the disclosing Party prompt notice of such requirement.

## 19.3  Permitted Disclosures

Notwithstanding Section 19.1, a Party may disclose Confidential Information to: (a) its Affiliates, directors, officers, employees, agents, advisors, and lenders, to the extent necessary for the performance of its obligations under this Agreement; and (b) potential assignees or transferees of its interest under this Agreement, subject to such recipients being bound by confidentiality obligations no less restrictive than those in this Article 19.

## 19.4  Duration

The obligations under this Article 19 shall survive the termination or expiration of this Agreement for a period of [five (5)] years.

# 20. MISCELLANEOUS PROVISIONS

## 20.1  Governing Law

This Agreement shall be governed by, construed and interpreted in accordance with the laws of the Federal Republic of Nigeria.

## 20.2  Entire Agreement

This Agreement, together with all Schedules and attachments, constitutes the entire agreement between the Parties with respect to the subject matter hereof and supersedes all prior agreements, negotiations, representations and understandings, whether written or oral.

## 20.3  Amendments

No provision of this Agreement may be amended, modified, waived or discharged except by an instrument in writing signed by both Parties.

## 20.4  Severability

If any provision of this Agreement is held to be invalid, void or unenforceable, the remaining provisions shall continue in full force and effect, and the Parties shall negotiate in good faith a valid replacement provision that achieves, to the extent possible, the economic, business and other purposes of the invalid provision.

## 20.5  Assignment

(a) Neither Party shall assign or transfer all or any part of its rights or obligations under this Agreement without the prior written consent of the other Party, such consent not to be unreasonably withheld.

(b) Notwithstanding the foregoing, the Owner may assign this Agreement to any of its Affiliates or to any lender or financial institution providing financing for the Project, without the Contractor’s consent.

(c) Any successor or assignee shall assume in writing all obligations of the assigning Party under this Agreement.

## 20.6  Notices

(a) All notices, requests, demands, consents and other communications required or permitted under this Agreement shall be in writing and shall be deemed duly given when delivered personally, sent by email (with confirmation of receipt), or sent by internationally recognized courier service to the addresses set forth below:

If to the Owner:

South Atlantic LNG West Africa Ltd, H20, Onikoyi Lane, Parkview Estate, Ikoyi, Lagos, Nigeria and info@southatlanticlng.com

If to the Contractor:

Peiyang Chemical Equipment Co. Ltd., 16B Zaire Crescent Maitama, Abuja, Nigeria and  africasale@peiyangchem.com

(b) Either Party may change its address for notice by giving written notice to the other Party in accordance with this Section.

## 20.7  No Waiver

The failure or delay of either Party to exercise any right, power, or remedy under this Agreement shall not operate as a waiver thereof, nor shall any single or partial exercise preclude any other or further exercise thereof.

## 20.8  Survival

The following provisions shall survive the termination or expiration of this Agreement: Article 10 (IP), Article 12 (Warranty), Article 13 (Liquidated Damages), Article 14 (Representations), Article 16 (Indemnification), Article 17 (Limitation of Liability), Article 18 (Dispute Resolution), Article 19 (Confidentiality), and this Section 20.8.

## 20.9  Priority of Documents

In the event of any conflict or inconsistency between the provisions of this Agreement and the Schedules, the following order of priority shall apply (in descending order): (a) the main body of this Agreement; (b) Schedule A-1 (Scope of Work); (c) Schedule A-2 (Basis of Design); (d) Schedule A-3 (Performance Guarantee and Tests); (e) Schedule E (Payment); and (f) all other Schedules.

## 20.10  Nigerian Content

The Parties shall comply with the requirements of the Nigerian Oil and Gas Industry Content Development Act 2010 and all applicable NCDMB regulations. The Contractor shall use reasonable efforts to maximize Nigerian content in the performance of the Work, including engagement of Nigerian Subcontractors, procurement of locally available materials, and employment and training of Nigerian nationals.

## 20.11  Anti-Corruption

Each Party represents and warrants that it has not made, and shall not make, any payment or give anything of value to any official of any Governmental Authority, any political party, or any other person in connection with this Agreement, for the purpose of obtaining or retaining business or securing any improper advantage, in violation of any anti-corruption law, including the Nigerian Corrupt Practices and Other Related Offences Act 2000, the UK Bribery Act 2010 and the US Foreign Corrupt Practices Act (to the extent applicable).

## 20.12  Language

This Agreement is executed in the English language. All correspondence, notices and documentation under this Agreement shall be in English.

## 20.13  Counterparts

This Agreement may be executed in any number of counterparts, each of which shall be deemed an original and all of which together shall constitute one and the same instrument.

## 20.14  Further Assurances

Each Party shall execute and deliver such further documents and take such further actions as may be reasonably necessary to give full effect to this Agreement.

## 20.15  Successors and Assigns

This Agreement shall be binding upon and inure to the benefit of the Parties and their respective successors and permitted assigns.

## 20.16  Lender Requirements

The Contractor acknowledges that the Owner may finance the Project through one or more lenders. The Contractor agrees to cooperate with the Owner and its lenders, including: (a) providing information and documentation reasonably required by the lenders; (b) entering into direct agreements or consents as may be reasonably required; and (c) permitting assignment of this Agreement to the lenders as security for the financing.

## 20.17  Independence from Financing Arrangements

The Contractor's obligations under this Agreement, including the obligation to complete the Work and achieve Substantial Completion by the Guaranteed Substantial Completion Date, are independent of and shall not be conditional upon or affected by any separate financing, credit, vendor loan or deferred payment arrangement between the Parties or their Affiliates. No dispute, default or event arising under any such separate arrangement shall entitle the Contractor to suspend, delay or modify the performance of the Work, nor shall it constitute a defence to any claim by the Owner under this Agreement.

SCHEDULES

The following Schedules are attached to and form an integral part of this Agreement. Unless otherwise indicated, each Schedule shall be prepared by the Contractor and submitted to the Owner for review and approval prior to or concurrent with execution of this Agreement.

## Schedule A-1: Scope of Work

To be prepared by the Contractor. This Schedule shall set forth the detailed Contractor’s scope of work and Owner’s scope of work, including:

(a) Engineering and design deliverables

(b) Equipment list and procurement responsibilities

(c) Logistics and transportation allocation (international shipping, port handling, customs, inland transport)

(d) Construction and installation scope

(e) Pre-commissioning, commissioning and start-up activities

(f) Documentation and training deliverables

(g) Owner’s scope and responsibilities

(h) Battery limits and interface points

(i) Specific exclusions from the Contractor’s scope

(j) Interface Responsibility Matrix — the Contractor shall prepare and maintain a detailed Interface Responsibility Matrix identifying responsibility for each physical, electrical, mechanical, process and control interface between Owner scope and Contractor scope, including all tie-in points, utility connections and handover specifications

## Schedule A-2: Basis of Design

To be prepared by the Contractor. This Schedule shall include:

(a) Site conditions (ambient temperature, humidity, wind, seismic, soil, elevation)

(b) Feedstock specifications (type, pressure, temperature, flow rate, composition)

(c) Product specifications

(d) Utility requirements (power, water, instrument air)

(e) Design codes and standards (Nigerian and international)

(f) List of FEED documents forming the basis for detailed design

## Schedule A-3: Performance Guarantee and Performance Test Procedures

To be prepared by the Contractor. This Schedule shall define:

(a) Guaranteed performance levels (capacity, product quality, efficiency, availability)

(b) Minimum Acceptance Criteria for each performance parameter

(c) Performance Test conditions, duration, and correction methodology

(d) Detailed Performance Test procedures

(e) Performance Liquidated Damages formulae

## Schedule B: Project Schedule and Key Milestones

To be prepared by the Contractor. This Schedule shall include:

(a) Key milestones table (benchmarked to NTP + Days)

(b) Guaranteed Substantial Completion Date

(c) Any project-specific conditions precedent to NTP

(d) Requirements for the detailed CPM schedule

## Schedule C: Site Description

To be prepared by the Owner. This Schedule shall include:

(a) Site location, address, GPS coordinates

(b) Total site area, construction area and laydown area

(c) Site plan, survey plan, access route map and geotechnical report summary

## Schedule D: Key Personnel

To be prepared by the Contractor. This Schedule shall include:

(a) List of Key Personnel positions with minimum experience requirements

(b) Proposed individuals and their CVs

## Schedule E: Contract Price and Payment Schedule

To be prepared by the Contractor and agreed with the Owner. This Schedule shall include:

(a) Total Contract Price and currency

(b) Contract Price breakdown by major component

(c) Payment milestone schedule with APG requirements

(d) Contractor’s bank details

(e) Liquidated Damages summary (Delay LD Rate, Delay LD Cap, Performance LD Cap, Combined LD Cap)

Payment Milestone Guidance:

Each milestone payment shall be tied to a verifiable physical deliverable or measurable event, not to time elapsed or percentage of engineering progress. Acceptable milestones include: delivery of major Equipment to port or Site (evidenced by bill of lading or delivery receipt); completion of defined civil works (evidenced by inspection report); mechanical completion of identified systems or units; and achievement of defined commissioning or testing events. The Contractor shall not front-load the payment schedule such that cumulative payments materially exceed the value of Work performed and Equipment delivered at any point during the Project.

## Schedule F: Insurance Requirements

To be prepared by the Contractor for Owner approval. This Schedule shall specify:

(a) Contractor’s required insurance types, minimum limits and deductibles

(b) Owner’s insurance (if applicable)

(c) General insurance requirements (additional insured, insurer ratings, waiver of subrogation)

Insurance Sizing Guidance:

The following minimum sizing principles shall apply when the Contractor proposes coverage limits:

(i) Construction All-Risk (CAR): minimum cover equal to the full reinstatement value of the Facility (not less than the Contract Price), including coverage for materials in transit and stored off-site;

(ii) Third Party Liability: minimum cover commensurate with the risk profile and location of the Project, taking into account proximity to populated areas, environmental sensitivity, and the nature of materials being handled;

(iii) Professional Indemnity: minimum cover commensurate with the Contractor’s design responsibility, with a run-off period of not less than twelve (12) months following Final Completion;

(iv) Marine Cargo: minimum 110% of the CIF value of each shipment;

(v) All insurers shall carry a minimum rating of A- (AM Best) or BBB+ (S&P) or equivalent; and

(vi) All deductibles shall be for the Contractor’s own account and shall not reduce the coverage available to the Owner.

## Schedule G: Form of Change Order

To be prepared by the Owner.

## Schedule J: Forms of Completion Certificates

To be prepared by the Owner.

## Schedule K: NCDMB / Nigerian Content Plan

To be prepared by the Contractor (where applicable). This Schedule shall include:

(a) Nigerian content targets by category (engineering, fabrication, procurement, manpower, subcontracting)

(b) Quarterly reporting requirements

SCHEDULE I: FORMS OF PERFORMANCE SECURITY

SCHEDULE I-1: FORM OF ADVANCE PAYMENT GUARANTEE

IRREVOCABLE BANK GUARANTEE — ADVANCE PAYMENT

(Subject to URDG 758)

Guarantee No.:          ___________

Date of Issue:          ___________

Issuing Bank:           [Bank Name and Address]

Beneficiary:            [Owner Entity Name and Address]

Applicant:              [Contractor Entity Name and Address]

Underlying Relationship: EPC Agreement dated [___] between the Beneficiary and the Applicant for the [Project Name] (the “Underlying Agreement”)

Guarantee Amount:       [Currency] [Amount in figures] ([Amount in words])

Being the amount of advance/milestone payment(s) under Article 7 of the Underlying Agreement.

We, [Bank Name] (the “Guarantor”), hereby irrevocably undertake to pay the Beneficiary any amount or amounts not exceeding in aggregate the Guarantee Amount, upon receipt by us of the Beneficiary’s complying demand.

A demand under this Guarantee shall be supported by the Beneficiary’s statement (whether in the demand itself or in a separate signed document accompanying or identifying the demand) indicating in what respect the Applicant is in breach of its obligations under the Underlying Agreement.

The Guarantee Amount shall be automatically reduced by the amounts specified in any reduction certificate(s) issued by the Beneficiary to us, confirming the value of Work performed or Equipment delivered by the Applicant against the relevant advance/milestone payment.

Expiry Date:            [___] or upon the Guarantee Amount being reduced to zero, whichever is earlier.

This Guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758.

_________________________________________

For and on behalf of [Bank Name]

Authorized Signatory

Name:   ________________________

Title:  ________________________

SCHEDULE I-2: FORM OF PERFORMANCE BOND

IRREVOCABLE BANK GUARANTEE — PERFORMANCE

(Subject to URDG 758)

Guarantee No.:          ___________

Date of Issue:          ___________

Issuing Bank:           [Bank Name and Address]

Beneficiary:           South Atlantic LNG West Africa Ltd and H20, Onikoyi Lane, Parkview Estate, Ikoyi, Lagos, Nigeria

Applicant:           Peiyang Chemical Equipment Co. Ltd.and 16B Zaire Crescent Maitama, Abuja, Nigeria

Underlying Relationship: EPC Agreement dated [___] between the Beneficiary and the Applicant for the 5MMSCFD Mini-LNG Gas Project (the “Underlying Agreement”)

Guarantee Amount:       [Currency] [Amount in figures] ([Amount in words])

Being [10]% of the Contract Price under the Underlying Agreement.

We, [Bank Name] (the “Guarantor”), hereby irrevocably undertake to pay the Beneficiary any amount or amounts not exceeding in aggregate the Guarantee Amount, upon receipt by us of the Beneficiary’s complying demand.

A demand under this Guarantee shall be supported by the Beneficiary’s statement (whether in the demand itself or in a separate signed document accompanying or identifying the demand) indicating in what respect the Applicant is in breach of its obligations under the Underlying Agreement.

This Guarantee covers the Applicant’s obligations during the construction phase of the Project, from the date of issuance through to Substantial Completion of the Facility, including but not limited to the Applicant’s obligations to achieve Mechanical Completion, complete Commissioning, pass the Performance Test and achieve Substantial Completion by the Guaranteed Substantial Completion Date.

Expiry Date:            [twenty-eight (28)] Days after the date of Substantial Completion under the Underlying Agreement, provided that this Guarantee shall not expire if a complying demand has been received by us on or before the Expiry Date.

Extension:              If the Expiry Date requires extension, the Applicant shall procure such extension and deliver evidence thereof to the Beneficiary not later than [thirty (30)] Days before the scheduled Expiry Date. If the Applicant fails to extend this Guarantee, the Beneficiary shall be entitled to make a demand under this Guarantee.

This Guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758.

_________________________________________

For and on behalf of [Bank Name]

Authorized Signatory

Name:   ________________________

Title:  ________________________

SCHEDULE I-3: FORM OF RETENTION BOND

IRREVOCABLE BANK GUARANTEE — RETENTION / WARRANTY

(Subject to URDG 758)

Guarantee No.:          ___________

Date of Issue:          ___________

Issuing Bank:           [Bank Name and Address]

Beneficiary:         South Atlantic LNG West Africa Ltd, and H20, Onikoyi Lane, Parkview Estate, Ikoyi, Lagos, Nigeria

Applicant:           Peiyang Chemical Equipment Co. Ltd., and 16B Zaire Crescent Maitama, Abuja, Nigeria

Underlying Relationship: EPC Agreement dated [___] between the Beneficiary and the Applicant for the 5MMSCFD Mini-LNG Gas Project  (the “Underlying Agreement”)

Guarantee Amount:       [Currency] [Amount in figures] ([Amount in words])

Being [5]% of the Contract Price under the Underlying Agreement.

We, [Bank Name] (the “Guarantor”), hereby irrevocably undertake to pay the Beneficiary any amount or amounts not exceeding in aggregate the Guarantee Amount, upon receipt by us of the Beneficiary’s complying demand.

A demand under this Guarantee shall be supported by the Beneficiary’s statement (whether in the demand itself or in a separate signed document accompanying or identifying the demand) indicating in what respect the Applicant is in breach of its post-Substantial Completion obligations under the Underlying Agreement.

This Guarantee covers the Applicant’s obligations during the Defect Correction Period and until Final Completion, including but not limited to: correction of Defects; completion of Punchlist items; compliance with Warranty obligations under Article 12 of the Underlying Agreement; and payment of any Performance Liquidated Damages.

Expiry Date:            [twenty-eight (28)] Days after the later of: (a) Final Completion under the Underlying Agreement; and (b) expiry of the Defect Correction Period (including any extensions pursuant to Section 12.2(c) of the Underlying Agreement).

Extension:              If the Defect Correction Period is extended in respect of any repaired or replaced item, the Applicant shall procure a corresponding extension of this Guarantee. If the Applicant fails to extend this Guarantee, the Beneficiary shall be entitled to make a demand under this Guarantee.

This Guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758.

_________________________________________

For and on behalf of [Bank Name]

Authorized Signatory

Name:   ________________________

Title:  ________________________

EXECUTION

IN WITNESS WHEREOF, the Parties have caused this Agreement to be executed and delivered by their duly authorized representatives as of the date first written above.

FOR AND ON BEHALF OF THE OWNER:

SOUTH ATLANTIC LNG WEST AFRICA LIMITED

_________________________________________

Authorized Signature

Name: _________________________________

Title: __________________________________

Date: __________________________________

WITNESS:

_________________________________________

Authorized Signature

Name: _________________________________

Title: __________________________________

Date: __________________________________

FOR AND ON BEHALF OF THE CONTRACTOR:

PEIYANG CHEMICAL EQUIPMENT CO. LTD.

_________________________________________

Authorized Signature

Name: _________________________________

Title: __________________________________

Date: __________________________________

WITNESS:

_________________________________________

Authorized Signature

Name: _________________________________

Title: __________________________________

Date: __________________________________